## Attachment 1
Attachment 1 - project pipeline as at 30 September 2024
Bedrooms
Street name | Location | Territorial Authority (TLA) | Project Stage | Project Status | Delivery Method | Resource Consent Approved | Building Consent Approved | Resource Consent Approved Date | Building Consent Approved Date | Construction Start Date | Expected Delivery Date | Building type | New Homes | 0/Bedsit | 1 | 2 | 3 | 4 | 5 | 6+ | Use of home | Forecast Building Cost
Tyler Street | Rangiora | Waimakariri District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-04 | 2023-11-15 | 2024-06-10 | 2024-12-02 | House | 1 |  |  | 1 |  |  |  |  | State | 645381.18
Pooks Road | Ranui | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-02 |  | 2025-02-18 | 2025-06-30 | House | 1 |  |  |  | 1 |  |  |  | State | 679250
Earlsworth Road | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-04 | 2024-03-13 |  | 2025-01-28 | House | 1 | [5 empty] | 1 |  | State | 689786.229
Landon Avenue | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-01 | 2024-04-23 |  | 2025-01-28 | House | 2 |  |  |  | 1 | 1 |  |  | State | 689786.229
Albionvale Road | Glen Eden | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-07-03 | 2024-07-23 | 2024-12-05 | 2025-05-28 | House | 1 |  |  |  | 1 |  |  |  | State | 699724.61
Danube Lane | Glen Eden | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-06-24 | 2024-12-02 | House | 1 |  |  |  | 1 |  |  |  | State | 737100
Wavell Street | Hastings | Hastings District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-09-02 | 2024-09-23 | 2025-02-18 | 2025-06-30 | House | 1 |  |  |  |  | 1 |  |  | State | 932580
Oban St, Mosgiel | Dunedin | Dunedin City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-11 | 2023-10-03 | 2024-05-28 | 2025-01-24 | House | 2 |  |  |  | 1 | 1 |  |  | State | 940710.85
Masters Place | Kaitaia | Far North District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-06-14 | 2024-09-04 |  | 2025-06-30 | House | 2 |  |  | 2 |  |  |  |  | State | 941274.28
Abbott Street | Gisborne | Gisborne District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-10-27 | 2024-03-08 |  | 2025-06-26 | House | 2 |  |  |  | 1 |  | 1 |  | State | 974969.42
Norrie Place | Napier | Napier City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-04-30 | 2025-06-30 | House | 2 |  | 1 |  |  | 1 |  |  | State | 995280
Girling Avenue | Blenheim | Marlborough District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2024-04-24 | 2024-04-04 |  | 2025-05-20 | House | 3 |  |  | 3 |  |  |  |  | State | 1009544.12
Seafield Place | New Brighton | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-01-19 | 2024-03-25 |  | 2025-05-30 | House | 2 |  |  | 2 |  |  |  |  | State | 1010231.99
Creek Road | Ashburton | Ashburton District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-06-19 | 2023-12-07 | 2024-04-11 | 2024-11-11 | House | 3 |  | 3 | [5 empty] | State | 1015396.4
Tyler Street | Rangiora | Waimakariri District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-13 |  | 2024-02-26 | 2024-11-20 | House | 3 |  | 3 | [5 empty] | State | 1074354
Galbraith Street | Ashburton | Ashburton District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-15 | 2024-01-19 | 2024-04-15 | 2025-02-20 | House | 3 |  | 3 | [5 empty] | State | 1092064.35
Chaucer Place | Owhata | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-07-30 | 2025-06-30 | Mixed | 3 |  | 3 | [5 empty] | State | 1130615.5556
Windsor Street | Opotiki | Opotiki District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-05-15 | 2024-07-23 | 2024-11-19 | 2025-03-26 | House | 3 |  | 2 | 1 |  |  |  |  | State | 1131030
Miller road | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-03-11 |  | 2024-07-29 | 2025-01-16 | House | 2 |  |  |  | 1 | 1 |  |  | State | 1134639.5193
Hobson Street | Kawerau | Kawerau District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-11-06 | 2024-01-22 | 2024-09-11 | 2025-01-14 | House | 2 |  |  | 2 |  |  |  |  | State | 1169772.82
Frostbite Pl | Ranui | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-07-24 | 2025-06-30 | House | 2 |  |  |  | 2 |  |  |  | State | 1170300
Beech Place | Owhata | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-07-30 | 2024-11-20 | House | 3 |  | 3 | [5 empty] | State | 1185419.6296
Brecon Road | Stratford | Stratford District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-12-15 | 2024-03-19 | 2024-08-07 | 2025-01-23 | Mixed | 3 | 2 | 1 | [5 empty] | State | 1194930
Kerrs Road | Linwood | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-09-19 | 2023-12-20 |  | 2025-05-30 | House | 3 |  | 3 | [5 empty] | State | 1226188.01
Sunrise Avenue | Owhata | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-06-17 | 2024-11-20 | House | 3 |  | 2 | 1 |  |  |  |  | State | 1247731.1111
Alastair Avenue | Owhata | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-07-30 | 2024-11-20 | House | 3 |  | 3 | [5 empty] | State | 1249983.3333
Ranolf Street | Glenholme | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-04-08 |  |  | 2025-05-02 | House | 2 |  |  |  | 2 |  |  |  | State | 1250536.63
Marsden Road | Nelson | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-05-29 | House | 3 |  | 3 | [5 empty] | State | 1256786
Rimu Street | Glenholme | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-06-10 | House | 2 |  |  |  | 1 | 1 |  |  | State | 1272930.75
Pedlar Street | Mangakakahi | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-07-30 | 2024-11-20 | Mixed | 3 |  | 2 | 1 |  |  |  |  | State | 1273256.2963
Wrantage Street | New Plymouth | New Plymouth District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-06-26 | 2025-06-30 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State | 1276580
Albertson Avenue | Dunedin | Dunedin City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-14 | 2023-05-10 | 2023-11-22 | 2024-11-01 | House | 2 |  |  | 2 |  |  |  |  | State | 1307397.67
De Costa Avenue | Gisborne | Gisborne District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-12-20 | 2024-03-05 |  | 2025-04-10 | House | 2 |  |  |  | 2 |  |  |  | State | 1317661.29
Romilly Street | Westport | Buller District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-15 | 2023-10-06 | 2024-03-19 | 2024-11-01 | House | 1 |  |  | 1 |  |  |  |  | State | 1322943.74
Romilly Street | Westport | Buller District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-15 | 2023-10-06 | 2024-03-19 | 2024-11-01 | House | 2 |  |  | 2 |  |  |  |  | State | 1322943.74
Huxley Road | Gisborne | Gisborne District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-12 |  |  | 2025-06-17 | House | 2 |  |  |  | 2 |  |  |  | State | 1323879.99
Valley Road | Gisborne | Gisborne District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-05-15 | 2025-06-30 | House | 3 |  | 1 |  | 2 |  |  |  | State | 1326520
Cain Street | Timaru | Timaru District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-18 | 2024-03-08 | 2024-06-17 | 2024-11-28 | House | 3 | 1 | 2 | [5 empty] | State | 1327961.01
McCullough Street | Mt Roskill | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2019-07-23 | 2020-03-12 |  | 2024-12-12 | House | 1 |  |  |  | 1 |  |  |  | State | 255502
Pandora Avenue | Sunnybrook | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-01-06 | 2025-05-05 | House | 3 |  | 2 |  | 1 |  |  |  | State | 1358840.7407
Stanley Road | Gisborne | Gisborne District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-05-02 | 2025-06-30 | House | 3 |  | 2 | 1 |  |  |  |  | State | 1359990
Coldstream Road | Gisborne | Gisborne District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-05-02 | 2025-06-30 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State | 1373600
Olsen Ave | Hillsborough | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2022-09-14 | 2024-09-16 | 2025-02-11 | 2025-06-30 | Mixed | 2 |  |  |  | 1 | 1 |  |  | State | 1375140
Astrolabe Street | Porirua | Porirua City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-31 | 2023-07-26 | 2023-07-11 | 2025-03-31 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 1379433
Valley Road | Gisborne | Gisborne District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-05-15 | 2025-06-30 | House | 3 |  | 2 | 1 |  |  |  |  | State | 1384000
Delphi Place | Sunnybrook | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-01-06 | 2025-05-05 | House | 3 |  | 2 | 1 |  |  |  |  | State | 1424155.1852
Winter Street | Gisborne | Gisborne District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2024-05-30 | 2024-06-25 | 2024-07-15 | 2024-12-12 | Mixed | 3 |  | 2 | 1 |  |  |  |  | State | 1425736
Mount View Drive | Mangakakahi | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-07-30 | 2024-11-20 | Mixed | 3 |  | 2 | 1 |  |  |  |  | State | 1430161.1111
Deborah Place | Mangakakahi | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-11 | 2024-04-08 | 2024-11-04 | 2025-04-11 | Mixed | 3 |  | 3 | [5 empty] | State | 1437668.5185
Fleet Street | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-03 | 2023-11-21 | 2024-06-24 | 2024-12-02 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State | 1457294.84
Princes Street | Ashburton | Ashburton District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-14 | 2024-02-12 |  | 2025-05-30 | House | 3 |  |  | 3 |  |  |  |  | State | 1460900.02
Windsor Street | Opotiki | Opotiki District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-05-15 | 2024-08-02 | 2024-11-12 | 2025-04-02 | House | 3 |  | 1 | 2 |  |  |  |  | State | 1488160
Hetherington Rd | Ranui | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-07-15 | 2025-06-30 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State | 1493250
Alison Street | Mangakakahi | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-04-24 | 2024-05-20 | 2025-01-27 | 2025-06-24 | House | 3 |  | 2 |  | 1 |  |  |  | State | 1502232.2222
Manuka Street | Gisborne | Gisborne District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-07-01 | 2024-07-22 | 2024-10-28 | 2025-03-18 | Mixed | 3 |  | 2 | 1 |  |  |  |  | State | 1507765.32
Sewell Street | Linwood | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-10 | 2023-08-28 | 2024-03-04 | 2024-11-18 | Duplex | 2 |  | 2 | [5 empty] | State | 1526469.08
Sewell Street | Linwood | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-10 | 2023-08-28 | 2024-03-04 | 2024-11-18 | House | 2 |  | 2 | [5 empty] | State | 1526469.08
Kowhai Street | Gisborne | Gisborne District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-09 |  | 2025-03-26 | 2025-06-30 | House | 3 |  | 1 | 2 |  |  |  |  | State | 1528020
Dido Place | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-02-19 | 2024-05-08 |  | 2025-04-30 | Duplex | 2 |  |  |  |  | 2 |  |  | State | 1544983.61
Wayside Avenue | Burnside | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-08 | 2023-06-02 | 2024-08-12 | 2025-06-27 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 379524.95
Wayside Avenue | Burnside | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-08 | 2023-06-02 | 2024-08-12 | 2025-06-27 | House | 1 | [5 empty] | 1 |  | State
Turquoise Place | Pukehangi | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-05-13 | 2024-07-17 | 2024-12-09 | 2025-05-20 | House | 3 |  | 2 |  | 1 |  |  |  | State | 1549528.8889
Massey Avenue | Greenlane | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-24 | 2023-12-19 | 2024-04-08 | 2025-01-22 | House | 2 |  |  |  | 2 |  |  |  | State | 1551830
Justine Street | Porirua | Porirua City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-16 | 2023-07-07 | 2023-07-20 | 2025-03-31 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 1553625
Bellona Place | Porirua | Porirua City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-16 | 2023-07-19 | 2023-06-26 | 2025-03-31 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 1553625
Valonia Street | New Windsor | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-06 | 2024-05-07 | 2024-05-28 | 2024-11-29 | House | 2 |  |  |  |  | 2 |  |  | State | 1587858.46
Leslie Avenue | Western Heights | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-14 | 2024-04-24 | 2024-11-04 | 2025-04-11 | House | 3 |  | 2 |  | 1 |  |  |  | State | 1599077.7778
Waiari Road | Takanini | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-07-08 | 2023-11-28 | 2024-03-04 | 2025-02-07 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 1648725.28
Waiari Road | Takanini | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-07-08 | 2023-11-28 | 2024-03-04 | 2025-02-07 | House | 1 |  |  |  | 1 |  |  |  | State | 1648725.28
Reeve Road | Owhata | Rotorua District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-03-20 | 2024-07-03 | 2024-07-30 | 2024-11-20 | House | 3 |  | 2 |  |  | 1 |  |  | State | 1661400
Collie Drive | Pukehangi | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-07-01 | 2024-12-03 | House | 3 |  |  | 1 | 2 |  |  |  | State | 1709436.6667
Willowpark Rd North | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-27 | 2024-03-06 | 2024-09-23 | 2025-02-14 | House | 3 |  |  | 2 | 1 |  |  |  | State | 1763883.79
Galbraith Street | Ashburton | Ashburton District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-14 | 2023-12-06 | 2024-04-15 | 2025-02-19 | House | 5 |  | 5 | [5 empty] | State | 1772541.75
Busby Street | Blockhouse Bay | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-26 | 2024-07-04 | 2024-07-29 | 2025-02-24 | House | 2 |  |  |  | 1 | 1 |  |  | State | 1817059
Amohau Street & Eruera | Rotorua | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-04-16 | 2024-08-12 |  | 2025-04-15 | House | 3 |  |  |  | 3 |  |  |  | State | 1875405.39
Gordon Road | Hastings | Hastings District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-06-13 | 2025-06-30 | House | 4 |  | 2 | 1 |  | 1 |  |  | State | 1889080
Barcroft Place | Clendon Park | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-05-21 | 2024-07-26 | 2024-09-09 | 2025-02-26 | Mixed | 3 |  |  |  | 3 |  |  |  | State | 1894750
Lowe Street | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-20 | 2024-04-22 | 2024-05-06 | 2024-11-29 | House | 3 |  |  | 1 | 1 | 1 |  |  | State | 1916781.08
Albertson Avenue | Dunedin | Dunedin City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-14 | 2023-05-25 | 2023-11-22 | 2025-02-13 | Duplex | 4 |  | 2 | 2 |  |  |  |  | State | 1952429.78
Boundary Road | Nelson | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-12-09 | 2025-05-06 | Mixed | 4 |  | 2 | 2 |  |  |  |  | State | 1963080
Huia Street | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-09 | 2024-03-18 | 2024-04-02 | 2024-11-29 | House | 3 |  |  |  |  | 3 |  |  | State | 1973541.16
De Costa Avenue | Gisborne | Gisborne District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-11-10 | 2024-03-05 |  | 2025-04-10 | House | 3 |  |  |  | 3 |  |  |  | State | 1977813.92
Frances Street | Ngongataha | Rotorua District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-12-12 | 2023-12-22 | 2023-11-13 | 2025-01-21 | Mixed | 3 |  | 2 | 1 |  |  |  |  | State | 2001650
Steeles Lane | Western Heights | Rotorua District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-01-19 | 2024-01-17 | 2024-05-27 | 2024-10-16 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State | 2040220
Doon Street | Mosgiel | Dunedin City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-01-31 | 2023-08-29 | 2024-02-21 | 2024-11-22 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 2109316.48
Doon Street | Mosgiel | Dunedin City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-01-31 | 2023-08-29 | 2024-02-21 | 2024-11-22 | House | 2 |  |  | 2 |  |  |  |  | State | 2109316.48
Balneavis Pl & Brabant Street | Opotiki | Opotiki District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-05-15 | 2024-07-25 | 2024-11-05 | 2025-04-28 | Mixed | 5 |  | 1 | 2 | 2 |  |  |  | State | 2144910
Haselden Street | Westport | Buller District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-18 |  |  | 2025-05-15 | House | 4 |  |  | 4 |  |  |  |  | State | 2179756.99
Galbraith Street | Ashburton | Ashburton District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-14 | 2023-11-22 | 2024-05-30 | 2025-04-10 | House | 6 |  | 4 | 2 |  |  |  |  | State | 2199579.34
Rewi Street | Te Awamutu | Waipa District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-09-13 | 2023-07-20 |  | 2025-05-14 | House | 3 |  |  | 2 | 1 |  |  |  | State | 2321443.82
Rewi Street | Te Awamutu | Waipa District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-09-13 | 2023-07-20 |  | 2025-05-14 | House | 1 |  |  |  | 1 |  |  |  | State | 2321443.82
Heath Street | Hamilton | Hamilton City | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-07-12 | 2024-01-03 |  | 2025-04-30 | Duplex | 4 |  |  |  | 4 |  |  |  | State | 2331043.92
Burgess St | Dunedin | Dunedin City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-15 | 2024-01-31 | 2024-09-02 | 2025-02-28 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 2355751.98
Burgess St | Dunedin | Dunedin City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-15 | 2024-01-31 | 2024-09-02 | 2025-02-28 | House | 2 |  | 1 | 1 |  |  |  |  | State | 2355751.98
Aurea Avenue | Pakuranga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-23 | 2023-07-06 | 2023-11-27 | 2024-10-31 | House | 1 |  |  |  |  | 1 |  |  | State | 2368694.27
Aurea Avenue | Pakuranga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-23 | 2023-07-06 | 2023-11-27 | 2025-03-31 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 2368694.27
Todd Place | Otahuhu | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-05-21 |  | 2024-11-27 | 2025-06-10 | Mixed | 5 |  | 4 |  | 1 |  |  |  | State | 2392247.25
St Georges Road | Avondale | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-07-29 | 2025-06-30 | Duplex | 4 |  |  | 4 |  |  |  |  | State | 2485080
Tucker Street | Ashburton | Ashburton District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-10 | 2023-11-23 | 2024-04-17 | 2025-01-20 | House | 6 |  |  | 3 | 2 | 1 |  |  | State | 2521676.01
Parkdale Cres | Kaitaia | Far North District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-02-04 | 2022-12-08 | 2024-04-22 | 2025-04-30 | House | 3 |  |  |  |  | 1 | 2 |  | State | 2534824
Budge Street | Blenheim | Marlborough District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-07 | 2023-12-19 | 2024-02-16 | 2024-11-18 | House | 4 |  |  | 3 | 1 |  |  |  | State | 2584940
Flay Cres | Burnside | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-03 | 2023-06-15 | 2024-08-15 | 2025-05-29 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 2610852.33
Flay Cres | Burnside | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-03 | 2023-06-15 | 2024-08-15 | 2025-05-29 | House | 1 |  |  |  | 1 |  |  |  | State | 2610852.33
Flay Cres | Burnside | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-03 | 2023-06-15 | 2024-08-15 | 2025-05-29 | Terrace | 3 |  |  | 3 |  |  |  |  | State
Selwyn Street | Timaru | Timaru District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-01-13 | 2025-06-09 | Mixed | 6 |  | 4 | 2 |  |  |  |  | State | 2631860
Clyde Road | Bryndwr | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-20 | 2023-08-15 | 2024-03-15 | 2025-01-23 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 2687682.49
Clyde Road | Bryndwr | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-20 | 2023-08-15 | 2024-03-15 | 2025-01-23 | House | 3 |  |  |  | 1 | 2 |  |  | State | 2687682.49
Boyne Avenue | Northcote | Christchurch City | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-07-13 | 2023-10-06 | 2024-05-06 | 2024-11-29 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 2688763.38
Boyne Avenue | Northcote | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-13 | 2023-10-06 | 2024-05-06 | 2024-11-29 | House | 3 |  |  | 1 | 1 | 1 |  |  | State | 2688763.38
Hillary Crescent | Riccarton | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-03-22 | 2024-04-22 | 2024-06-05 | 2024-11-13 | Mixed | 6 |  | 6 | [5 empty] | State | 2748236.31
Hoffman Street | Hokitika | Westland District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-09-12 | 2024-02-26 |  | 2025-06-30 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 2752514.53
Hoffman Street | Hokitika | Westland District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-09-12 | 2024-02-26 |  | 2025-06-30 | House | 3 |  |  |  | 2 | 1 |  |  | State | 2752514.53
Momorangi Cres | Redwood | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-28 | 2024-02-27 | 2024-07-08 | 2024-12-11 | Mixed | 6 |  | 4 | 2 |  |  |  |  | State | 2759582.01
Ruth Street | Fordlands | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-05-07 | 2024-07-02 | 2025-01-06 | 2025-06-16 | Duplex | 6 |  | 4 |  | 2 |  |  |  | State | 2831043.3333
Graham Street | Blenheim | Marlborough District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-16 | 2023-11-06 | 2024-04-15 | 2024-11-28 | Duplex | 4 |  |  | 4 |  |  |  |  | State | 2842612.94
Graham Street | Blenheim | Marlborough District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-16 | 2023-11-06 | 2024-04-15 | 2024-11-28 | House | 1 | [5 empty] | 1 |  | State | 2842612.94
Grange Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-03 | 2023-09-01 | 2024-02-26 | 2025-01-29 | Duplex | 6 |  |  | 6 |  |  |  |  | State | 2904324.88
MacDonald Street | Gisborne | Gisborne District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-03-14 | 2025-06-30 | House | 6 |  | 3 | 3 |  |  |  |  | State | 2962500
Albrecht Avenue & Halleys Place | Mount Roskill | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-05-05 | 2025-06-30 | House | 5 |  |  | 3 | 2 |  |  |  | State | 2979250
Guildford Street | Burnside | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-03 | 2023-07-21 | 2024-02-12 | 2024-11-29 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Guildford Street | Burnside | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-03 | 2023-07-21 | 2024-02-12 | 2024-11-29 | House | 3 |  |  |  |  | 2 | 1 |  | State
Balmoral Road | Whangarei | Whangarei District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2024-07-02 | 2024-08-08 | 2024-09-24 | 2025-06-27 | House | 5 |  |  | 3 |  | 2 |  |  | State | 2997125.01
Kingsway Avenue | Sandringham | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-25 | 2024-03-21 | 2024-02-13 | 2024-10-31 | Walk-up | 6 |  |  | 6 |  |  |  |  | Transitional | 3042739.24
Denbigh Avenue & Somerset Road | Mount Roskill | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-08-26 | 2025-06-30 | House | 6 |  |  | 4 | 2 |  |  |  | State | 3085660
Tyler Street | Rangiora | Waimakariri District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-01-15 | 2024-03-19 | 2024-05-20 | 2024-11-14 | Mixed | 7 |  | 4 | 1 | 1 | 1 |  |  | State | 3167076.01
Kawaha Point Road | Kawaha Point | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-05-06 | 2024-07-02 | 2024-12-09 | 2025-05-20 | Mixed | 6 |  | 4 |  |  | 2 |  |  | State | 3225932.963
Lowry Terrace | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-05 |  |  | 2025-06-26 | Duplex | 6 |  |  | 4 | 2 |  |  |  | State | 3272339.01
Hewer Cres | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-08 | 2023-10-18 | 2024-03-27 | 2025-01-30 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 3277486.26
Hewer Cres | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-08 | 2023-10-18 | 2024-03-27 | 2025-01-30 | House | 2 |  |  |  |  | 1 |  | 1 | State
Lovatt Cres | Whangarei | Whangarei District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-03-07 | 2024-02-01 | 2024-08-05 | 2025-03-31 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 3321578.42
Lovatt Cres | Whangarei | Whangarei District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-03-07 | 2024-02-01 | 2024-08-05 | 2025-03-31 | Terrace | 3 |  |  | 3 |  |  |  |  | State
Aliford Street | One Tree Hill | Auckland | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-07-24 | 2024-07-31 | 2024-09-16 | 2025-05-27 | Mixed | 4 |  |  |  |  | 2 | 2 |  | State | 3337808.44
Hazelmere Crescent | Te Awamutu | Waipa District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2022-11-02 | 2022-10-15 |  | 2025-04-08 | House | 6 |  |  | 3 | 3 |  |  |  | State | 3349277.35
Stewart Street | Whakatane | Whakatane District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-31 | 2023-11-06 | 2024-06-17 | 2025-02-18 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State | 3371046.03
Stewart Street | Whakatane | Whakatane District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-31 | 2023-11-06 | 2024-06-17 | 2025-02-18 | House | 2 |  |  |  |  | 2 |  |  | State
Finlayson Avenue | Clendon Park | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-02-21 | 2023-05-05 | 2024-04-11 | 2025-01-24 | Duplex | 2 | [5 empty] | 2 |  | State | 3403723.6
Finlayson Avenue | Clendon Park | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-02-21 | 2023-05-05 | 2024-04-11 | 2025-01-24 | House | 2 |  |  |  |  | 1 | 1 |  | State | 3403723.6
Mountford Street & Claymore Street | Manurewa | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-13 | 2023-12-18 | 2024-02-19 | 2024-10-25 | House | 3 |  |  |  | 1 | 1 | 1 |  | State | 3426286
Mountford Street & Claymore Street | Manurewa | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-13 | 2023-12-18 | 2024-02-19 | 2024-11-28 | House | 1 |  |  |  |  | 1 |  |  | State | 3426286
Bucklands Beach Rd & Gills Road | Half Moon Bay | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-08-22 | 2023-02-20 | 2024-07-01 | 2025-06-30 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 3526720.76
Bucklands Beach Rd & Gills Road | Half Moon Bay | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-08-22 | 2023-02-20 | 2024-07-01 | 2025-06-30 | House | 1 |  |  |  |  | 1 |  |  | State | 3526720.76
Bucklands Beach Rd & Gills Road | Half Moon Bay | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-08-22 | 2023-02-20 | 2024-07-01 | 2025-06-30 | Terrace | 3 |  |  | 3 |  |  |  |  | State
Pallant Street | Manurewa | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-15 | 2024-03-24 | 2024-07-19 | 2025-02-21 | Mixed | 6 |  |  | 2 | 2 | 2 |  |  | State | 3542756
Boyne Avenue | Northcote | Christchurch City | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-08-01 | 2023-08-14 |  | 2025-05-02 | Duplex | 4 |  |  | 4 |  |  |  |  | State | 3551415.98
Boyne Avenue | Northcote | Christchurch City | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-08-01 | 2023-08-14 |  | 2025-05-02 | House | 2 |  |  |  |  | 2 |  |  | State | 3551415.98
Sapphire Street | Casebrook | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-01-31 | 2023-03-17 | 2024-04-24 | 2024-11-13 | Mixed | 8 |  | 6 |  | 2 |  |  |  | State | 3633285
Brighton Road | Dunedin | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-15 | 2024-05-30 |  | 2025-05-30 | Duplex | 8 |  | 1 | 7 |  |  |  |  | State | 3715951
Ward Street | Greymouth | Grey District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-06-13 | House | 8 |  |  | 8 |  |  |  |  | State | 3765097.12
Fawn St & Calliope Cres | Porirua | Porirua City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-17 | 2024-05-01 | 2024-08-02 | 2025-06-19 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State | 3787204.18
Fawn St & Calliope Cres | Porirua | Porirua City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-17 | 2024-05-01 | 2024-08-02 | 2025-06-19 | House | 3 |  |  |  | 1 | 2 |  |  | State | 3787204.18
Bedford Road & Lowry Tce | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-04-19 |  |  | 2025-06-06 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 3804935.99
Bedford Rd & Lowry Tce, Napier | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-04-19 |  |  | 2025-06-06 | House | 2 |  |  |  | 2 |  |  |  | State | 3804935.99
Bedford Rd & Lowry Tce, Napier | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-04-19 |  |  | 2025-06-06 | Terrace | 3 |  |  | 3 |  |  |  |  | State | 3804935.99
Wrigley Road | Fordlands | Rotorua District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-12-07 | 2024-03-04 | 2024-09-30 | 2025-04-23 | Mixed | 9 | 3 | 6 | [5 empty] | State | 3825032
Ford Road & Irene Place | Fordlands | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-06 | 2024-05-10 | 2024-10-07 | 2025-05-01 | Mixed | 9 |  | 7 | 1 | 1 |  |  |  | State | 3939042
Campbell Road & Massey Avenue | Greenlane | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-24 | 2023-05-12 | 2024-04-30 | 2025-06-30 | House | 2 |  |  |  |  | 2 |  |  | State | 3989169.72
Campbell Road & Massey Avenue | Greenlane | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-24 | 2023-05-12 | 2024-04-30 | 2025-06-30 | Terrace | 5 |  |  | 3 | 2 |  |  |  | State | 3989169.72
Pukuatua Street | Rotorua | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-03-07 |  | 2025-01-06 | 2025-06-30 | Mixed | 10 |  | 9 | 1 |  |  |  |  | State | 3990937.7778
Haukore Street | Hairini | Tauranga City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-14 | 2023-10-26 | 2023-11-07 | 2025-02-10 | House | 5 |  |  |  | 2 | 3 |  |  | State | 4020451.09
Manchester Street | Palmerston North | Palmerston North City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-22 | 2024-02-02 | 2024-02-02 | 2024-10-10 | Duplex | 4 |  |  | 2 |  | 2 |  |  | State | 4024943.81
Manchester Street | Palmerston North | Palmerston North City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-22 | 2024-02-02 | 2024-02-02 | 2024-10-10 | House | 2 |  |  |  |  | 1 | 1 |  | State | 4024943.81
Bledisloe Road | Napier | Napier City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-06-30 | Duplex | 2 |  |  |  |  | 2 |  |  | State | 4033324.01
Bledisloe Road | Napier | Napier City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-06-30 | House | 2 |  |  |  | 1 |  | 1 |  | State | 4033324.01
Bledisloe Road | Napier | Napier City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-06-30 | Terrace | 3 |  |  | 3 |  |  |  |  | State | 4033324.01
Puriri Cres | Hillcrest | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-12-15 | 2024-04-29 | 2024-11-11 | 2025-06-05 | Mixed | 8 |  | 2 | 5 | 1 |  |  |  | State | 4038234.4444
Waiwhetu Road | Lower Hutt | Lower Hutt City | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-05-25 | 2024-05-06 |  | 2025-04-30 | House | 6 |  |  | 3 | 3 |  |  |  | State | 4048588
Great South Road | Manurewa | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-10-04 | 2023-06-01 | 2023-10-10 | 2024-11-07 | Duplex | 2 |  |  | 2 |  |  |  |  | CGH | 4085894.06
Great South Road | Manurewa | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-10-04 | 2023-06-01 | 2023-10-10 | 2024-11-07 | Terrace | 6 |  |  | 6 |  |  |  |  | CGH | 4085894.06
Dido Pl & Calliope Cres | Porirua | Porirua City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-08-25 | 2024-05-20 | 2024-08-02 | 2025-06-19 | House | 7 |  |  |  | 2 | 5 |  |  | State | 4140464.55
Waiwhetu Road | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-06-20 | 2023-07-17 |  | 2025-06-25 | Duplex | 8 |  |  | 8 |  |  |  |  | State | 4193835.59
Korimako Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-29 | 2024-03-06 | 2024-03-13 | 2024-12-09 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 4215686.55
Korimako Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-29 | 2024-03-06 | 2024-03-13 | 2024-12-09 | House | 4 |  |  |  | 4 |  |  |  | State | 4215686.55
Breckons Avenue & Beatrice Pl | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-04 | 2023-08-08 | 2023-11-22 | 2024-11-15 | Duplex | 4 |  |  |  | 2 |  | 2 |  | State | 4316561.11
Breckons Avenue & Beatrice Pl | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-04 | 2023-08-08 | 2023-11-22 | 2024-11-15 | House | 1 |  |  |  |  | 1 |  |  | State | 4316561.11
Breckons Avenue & Beatrice Pl | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-04 | 2023-08-08 | 2023-11-22 | 2024-11-15 | Terrace | 3 |  |  | 3 |  |  |  |  | State | 4316561.11
Cowell Place | Onehunga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-27 | 2023-11-14 | 2024-01-16 | 2024-12-09 | Mixed | 6 |  |  | 3 | 3 |  |  |  | State | 4364989
Cottrell Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-13 | 2024-03-27 | 2024-04-02 | 2024-12-05 | Duplex | 2 |  |  |  |  | 2 |  |  | State | 4402200
Cottrell Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-13 | 2024-03-27 | 2024-04-02 | 2024-12-05 | House | 6 |  |  | 4 |  | 1 | 1 |  | State | 4402200
Redmond Street | Judea | Tauranga City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-26 | 2023-10-13 | 2024-04-29 | 2025-02-11 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 4415856.25
Redmond Street | Judea | Tauranga City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-26 | 2023-10-13 | 2024-04-29 | 2025-02-11 | House | 3 |  |  | 1 |  | 2 |  |  | State | 4415856.25
Redmond Street | Judea | Tauranga City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-26 | 2023-10-13 | 2024-04-29 | 2025-02-11 | Terrace | 3 |  |  | 3 |  |  |  |  | State | 4415856.25
Allens Road | Ashburton | Ashburton District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2024-03-18 | 2024-04-12 | 2024-09-30 | 2025-03-24 | Mixed | 9 |  | 6 | 1 | 2 |  |  |  | State | 4428995
Winstone Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-04 | 2023-06-21 | 2023-11-02 | 2024-11-29 | Walk-up | 8 |  |  | 4 | 4 |  |  |  | State | 4433113.77
McDivitt Street | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-19 |  | 2025-02-14 | 2025-06-30 | Mixed | 7 |  |  |  | 5 | 2 |  |  | State | 4500720
Rawlings - &Willis ,BaderHam | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-09 | 2023-06-20 | 2023-10-25 | 2024-11-14 | Duplex | 4 |  |  | 4 |  |  |  |  | State | 4628520.18
Rawlings - &Willis ,BaderHam | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-09 | 2023-06-20 | 2023-10-25 | 2024-11-14 | House | 4 |  |  |  | 2 | 2 |  |  | State | 4628520.18
Salmond Street | Hoon Hay | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-06-27 | 2023-12-21 | 2024-08-26 | 2025-02-25 | Mixed | 8 |  | 5 | 2 |  | 1 |  |  | State | 4701542.87
Clinkard Avenue | Glenholme | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-26 | 2024-06-04 | 2024-10-07 | 2025-05-01 | Mixed | 9 |  | 5 | 4 |  |  |  |  | State | 4703132
Bledisloe Road | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-07-28 |  |  | 2025-06-12 | House | 1 |  |  |  |  | 1 |  |  | State | 4812749.99
Bledisloe Road | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-07-28 |  |  | 2025-06-12 | Walk-up | 8 |  |  | 8 |  |  |  |  | State | 4812749.99
Cutler Cres & Arawa Rd | Whakatane | Whakatane District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-05-02 | 2024-05-15 | 2024-05-29 | 2024-12-13 | House | 10 |  | 5 | 4 | 1 |  |  |  | State | 4857649
Marion Avenue | Mount Roskill | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-26 | 2023-11-09 | 2024-04-15 | 2025-03-31 | Terrace | 9 |  |  | 7 | 2 |  |  |  | State | 4925327.59
Burlington Street | Sydenham | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-14 | 2024-03-22 | 2024-03-25 | 2024-12-06 | Walk-up | 14 |  | 14 | [5 empty] | State | 4972034.18
Seddon Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-12-14 | 2024-07-03 | 2024-09-02 | 2025-06-30 | Duplex | 8 |  |  | 8 |  |  |  |  | State | 4977739.83
Seddon Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-12-14 | 2024-07-03 | 2024-09-02 | 2025-06-30 | House | 2 |  |  |  |  | 2 |  |  | State | 4977739.83
Kern Place | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-25 |  | 2025-04-11 | 2025-06-30 | Mixed | 9 |  | 4 | 2 | 3 |  |  |  | State | 5042570
Kain Street | Mount Eden | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-02-18 | 2023-11-20 | 2024-04-29 | 2025-01-30 | Duplex | 4 |  |  |  |  | 2 | 2 |  | State | 5174416.14
Kain Street | Mount Eden | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-02-18 | 2023-11-20 | 2024-04-29 | 2025-01-30 | House | 1 | [6 empty] | 1 | State
Kain Street | Mount Eden | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-02-18 | 2023-11-20 | 2024-04-29 | 2025-06-30 | Duplex | 2 |  |  |  |  | 2 |  |  | State
Wairau Avenue & Riversdale Road | Avondale | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-06 | 2023-06-30 | 2024-07-08 | 2025-06-17 | Duplex | 2 |  |  |  |  | 2 |  |  | State | 5229582
Wairau Avenue & Riversdale Road | Avondale | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-06 | 2023-06-30 | 2024-07-08 | 2025-06-17 | Walk-up | 6 |  |  | 6 |  |  |  |  | State | 5229582
Hollyford Avenue | Bryndwr | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-02-14 | 2023-10-03 | 2024-05-06 | 2025-04-16 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 5292980.68
Hollyford Avenue | Bryndwr | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-02-14 | 2023-10-03 | 2024-05-06 | 2025-04-16 | House | 6 |  |  |  |  | 1 | 3 | 2 | State | 5292980.68
Raurenga Avenue | Royal Oak | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-07 | 2024-01-26 | 2024-07-01 | 2025-05-30 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 5322048.34
Raurenga Avenue | Royal Oak | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-07 | 2024-01-26 | 2024-07-01 | 2025-05-30 | House | 1 |  |  |  |  | 1 |  |  | State | 5322048.34
Raurenga Avenue | Royal Oak | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-07 | 2024-01-26 | 2024-07-01 | 2025-05-30 | Walk-up | 6 |  |  | 6 |  |  |  |  | State | 5322048.34
Baldwin Street | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-09 | 2024-01-30 | 2024-07-15 | 2025-05-23 | Duplex | 8 |  |  | 6 | 2 |  |  |  | State | 5354228.99
Baldwin Street | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-09 | 2024-01-30 | 2024-07-15 | 2025-05-23 | House | 1 |  |  |  |  | 1 |  |  | State | 5354228.99
Meadowbank Cres | Fordlands | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-18 | 2024-05-07 | 2024-10-21 | 2025-05-01 | Mixed | 10 |  | 5 | 4 | 1 |  |  |  | State | 5468656
Valentine St & Cargill St | Papakura | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-23 | 2024-03-15 | 2024-08-12 | 2025-06-25 | Duplex | 6 |  |  |  | 2 | 2 | 2 |  | State | 5569372.8
Valentine St & Cargill St | Papakura | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-23 | 2024-03-15 | 2024-08-12 | 2025-06-25 | House | 3 |  |  |  | 3 |  |  |  | State | 5569372.8
Cottrell Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-11 | 2024-03-12 | 2024-03-18 | 2025-02-04 | Duplex | 10 |  |  | 8 | 2 |  |  |  | State | 5726204.39
Cottrell Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-11 | 2024-03-12 | 2024-03-18 | 2025-02-04 | House | 3 |  |  |  | 2 | 1 |  |  | State | 5726204.39
Hukanui Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-04 | 2023-10-12 | 2024-06-20 | 2025-04-11 | Terrace | 4 |  |  | 4 |  |  |  |  | State | 5749956.66
Hukanui Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-04 | 2023-10-12 | 2024-06-20 | 2025-04-11 | Walk-up | 6 |  | 6 | [5 empty] | State | 5749956.66
Tania Cres | Western Heights | Rotorua District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-31 | 2023-11-14 | 2024-04-08 | 2024-11-26 | Mixed | 12 |  | 9 | 2 | 1 |  |  |  | State | 5842908
Mt Albert Road & Buckley Road | Royal Oak | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-16 | 2023-12-05 | 2024-04-26 | 2025-01-29 | Terrace | 4 |  |  | 2 | 2 |  |  |  | State | 6098940.05
Mt Albert Road & Buckley Road | Royal Oak | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-16 | 2023-12-05 | 2024-04-26 | 2025-01-29 | Walk-up | 6 |  |  | 6 |  |  |  |  | State | 6098940.05
Kettle Street | Pt Chevalier | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-02 | 2022-12-19 | 2023-11-23 | 2025-03-14 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 6120901.05
Kettle Street | Pt Chevalier | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-02 | 2022-12-19 | 2023-11-23 | 2025-03-14 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Kettle Street | Pt Chevalier | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-02 | 2022-12-19 | 2023-11-23 | 2025-03-14 | Duplex | 2 |  |  | 2 |  |  |  |  | State
Kettle Street | Pt Chevalier | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-02 | 2022-12-19 | 2023-11-23 | 2025-03-14 | House | 3 |  |  |  | 2 | 1 |  |  | State
Yeats Cres & Marshall St | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-22 | 2023-06-26 | 2023-11-13 | 2024-10-18 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 6219903.39
Yeats Cres & Marshall St | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-22 | 2023-06-26 | 2023-11-13 | 2024-10-18 | Duplex | 4 |  |  |  |  | 4 |  |  | State
Yeats Cres & Marshall St | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-22 | 2023-06-26 | 2023-11-13 | 2024-10-18 | House | 4 |  |  | 4 |  |  |  |  | State
Rautara Street | Orakei | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-21 |  | 2024-05-15 | 2025-05-06 | Walk-up | 12 |  | 12 | [5 empty] | State | 6496386
Hendon Avenue & Hargest Terrace | Mount Albert | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-06-10 | 2023-08-07 | 2022-10-18 | 2025-01-30 | Walk-up | 9 |  | 3 | 3 | 3 |  |  |  | State | 6511138.07
George Street | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-08 | 2023-05-19 | 2023-10-02 | 2024-10-30 | Duplex | 8 |  |  | 4 | 4 |  |  |  | State | 6569297.86
George Street | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-08 | 2023-05-19 | 2023-10-02 | 2024-10-30 | House | 1 | [5 empty] | 1 |  | State | 6569297.86
Venables Ave, Cornford Pl, Cottrell Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-08-11 | 2023-07-25 | 2023-11-13 | 2025-03-07 | Duplex | 10 |  |  | 10 |  |  |  |  | State | 6779300.71
Venables Ave, Cornford Pl, Cottrell Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-08-11 | 2023-07-25 | 2023-11-13 | 2025-03-07 | House | 3 |  |  | 1 | 1 |  | 1 |  | State | 6779300.71
Haukore Street | Hairini | Tauranga City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-22 | 2023-12-20 | 2024-05-10 | 2025-05-07 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 6862336.59
Haukore Street | Hairini | Tauranga City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-22 | 2023-12-20 | 2024-05-10 | 2025-05-07 | House | 2 |  |  |  | 2 |  |  |  | State
Haukore Street | Hairini | Tauranga City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-22 | 2023-12-20 | 2024-05-10 | 2025-05-07 | House | 3 |  |  |  | 2 | 1 |  |  | State
Haukore Street | Hairini | Tauranga City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-22 | 2023-12-20 | 2024-05-10 | 2025-05-07 | House | 4 |  |  |  | 1 | 3 |  |  | State
Humphrey Kemp Avenue | Henderson | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-11-29 | 2025-06-30 | Mixed | 12 |  | 6 | 4 | 2 |  |  |  | State | 6970480
Dobson Street | Ashburton | Ashburton District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-01 | 2023-12-04 | 2024-04-15 | 2024-12-05 | Mixed | 15 |  | 12 | 3 |  |  |  |  | State | 7056794
Lawrence Street | Te Kuiti | Waitomo District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-10 | 2024-05-30 | 2024-05-30 | 2025-03-06 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State | 7140304.12
Lawrence Street | Te Kuiti | Waitomo District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-10 | 2024-05-30 | 2024-05-30 | 2025-03-06 | House | 2 |  |  |  | 2 |  |  |  | State
Lawrence Street | Te Kuiti | Waitomo District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-11-10 | 2024-05-30 | 2024-05-30 | 2025-03-06 | Terrace | 5 |  |  | 3 | 2 |  |  |  | State
College Pl & Bankwood Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-06 | 2023-06-26 | 2024-01-23 | 2024-10-30 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 7186364.85
College Pl & Bankwood Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-06 | 2023-06-26 | 2024-01-23 | 2024-10-30 | Terrace | 10 |  |  | 6 | 4 |  |  |  | State | 7186364.85
Constable Cres | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-12-15 | 2024-08-05 |  | 2025-06-30 | Duplex | 2 |  |  |  |  | 2 |  |  | State | 7243681.85
Constable Cres | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-12-15 | 2024-08-05 |  | 2025-06-30 | House | 10 |  |  | 2 | 6 | 1 | 1 |  | State | 7243681.85
Bray Street & Smith Street | Woolston | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-14 | 2023-12-04 | 2024-05-27 | 2024-12-13 | Mixed | 13 |  | 6 | 4 | 3 |  |  |  | State | 7265939
Mahia Road | Wattle Downs | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-01 |  |  | 2025-06-30 | Duplex | 6 |  |  |  |  | 6 |  |  | State | 7280774.24
Mahia Road | Wattle Downs | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-01 |  |  | 2025-06-30 | Duplex | 4 |  |  |  |  | 4 |  |  | State
Mahia Road | Wattle Downs | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-01 |  |  | 2025-06-30 | House | 1 |  |  |  |  | 1 |  |  | State
Mahia Road | Wattle Downs | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-01 |  |  | 2025-06-30 | House | 1 |  |  |  |  | 1 |  |  | State
Stratford Street | Blenheim | Marlborough District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-27 | 2024-01-19 | 2024-05-20 | 2025-04-28 | Duplex | 8 |  |  | 6 | 2 |  |  |  | State | 7420161.1
Stratford Street | Blenheim | Marlborough District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-27 | 2024-01-19 | 2024-05-20 | 2025-04-28 | House | 5 |  |  |  | 1 | 2 | 2 |  | State
Edinburgh Avenue | Papakura | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-22 | 2023-05-17 | 2024-01-30 | 2025-01-31 | Duplex | 6 |  |  | 2 | 2 | 2 |  |  | State | 7424233.89
Edinburgh Avenue | Papakura | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-22 | 2023-05-17 | 2024-01-30 | 2025-01-31 | House | 4 |  |  |  | 2 | 1 | 1 |  | State
Edinburgh Avenue | Papakura | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-11-22 | 2023-05-17 | 2024-01-30 | 2025-01-31 | Terrace | 3 |  |  | 3 |  |  |  |  | State
Aquarius Drive & Virgo Place | Kawaha Point | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-04-02 | 2024-07-03 | 2024-10-07 | 2025-06-13 | Mixed | 13 |  | 4 | 4 | 4 | 1 |  |  | State | 7671248
Jollie Street & Nalder Place | Linwood | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-01 | 2024-06-11 | 2024-06-11 | 2025-06-17 | Duplex | 14 |  |  | 6 |  | 8 |  |  | State | 7838900.76
Jollie Street & Nalder Place | Linwood | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-01 | 2024-06-11 | 2024-06-11 | 2025-06-17 | House | 2 |  |  | 1 |  |  | 1 |  | State | 7838900.76
Clyde Street | Tokoroa | South Waikato District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-05-15 | 2024-07-04 | 2024-11-18 | 2025-06-18 | House | 13 |  | 8 | 4 | 2 |  |  |  | State | 7875630
Lister Crescent | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-06 | 2023-09-18 | 2024-04-11 | 2025-05-20 | Duplex | 12 |  |  | 12 |  |  |  |  | State | 7879516.98
Lister Crescent | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-09-06 | 2023-09-18 | 2024-04-11 | 2025-05-20 | House | 4 |  |  |  | 1 | 1 | 2 |  | State | 7879516.98
Beach Road | Te Atatu | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-17 | 2023-08-21 | 2023-12-13 | 2024-11-20 | Walk-up | 12 |  | 12 | [5 empty] | State | 8187623
Rawlings Street & Pine Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-25 | 2023-08-29 | 2023-08-29 | 2024-11-29 | Duplex | 8 |  |  | 2 |  | 4 | 2 |  | State | 8232028.12
Rawlings Street & Pine Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-25 | 2023-08-29 | 2023-08-29 | 2024-11-29 | House | 2 |  |  |  |  | 2 |  |  | State
Rawlings Street & Pine Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-25 | 2023-08-29 | 2023-08-29 | 2025-03-31 | House | 3 |  |  |  |  | 3 |  |  | State
Lambeth Road | Sandringham | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-10-31 | 2023-11-03 | 2024-06-10 | 2025-06-25 | Walk-up | 12 |  |  | 6 | 6 |  |  |  | State | 8642349.48
Wrantage Street & Holford Street | New Plymouth | New Plymouth District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-01 | 2023-10-26 | 2023-04-11 | 2024-12-11 | Duplex | 4 |  | 4 | [5 empty] | State | 8720737.61
Wrantage Street & Holford Street | New Plymouth | New Plymouth District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-01 | 2023-10-26 | 2023-04-11 | 2024-12-11 | Duplex | 4 |  | 4 | [5 empty] | State | 8720737.61
Venables Avenue & McLaren Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-23 | 2023-07-18 | 2023-12-13 | 2024-11-27 | Duplex | 8 |  |  | 6 |  | 2 |  |  | State | 8824865.81
Venables Avenue & McLaren Cres | Napier | Napier City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-23 | 2023-07-18 | 2023-12-13 | 2024-11-27 | House | 7 |  |  |  | 5 | 1 | 1 |  | State | 8824865.81
Franklyne Road & Raleigh Place | Otara | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-03-14 | 2025-06-30 | Mixed | 13 |  |  | 6 | 6 | 1 |  |  | State | 8856150
Kawaha Point Road | Kawaha Point | Rotorua District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-11-28 | 2023-12-07 | 2024-09-18 | 2025-06-27 | Duplex | 2 |  |  | 2 |  |  |  |  | State | 8898974.07
Kawaha Point Road | Kawaha Point | Rotorua District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-11-28 | 2023-12-07 | 2024-09-18 | 2025-06-27 | Duplex | 8 |  |  | 8 |  |  |  |  | State
Kawaha Point Road | Kawaha Point | Rotorua District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-11-28 | 2023-12-07 | 2024-09-18 | 2025-06-27 | House | 1 |  |  |  |  | 1 |  |  | State
Kawaha Point Road | Kawaha Point | Rotorua District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-11-28 | 2023-12-07 | 2024-09-18 | 2025-06-27 | House | 4 |  |  |  | 2 | 2 |  |  | State
Kawaha Point Road | Kawaha Point | Rotorua District | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2023-11-28 | 2023-12-07 | 2024-09-18 | 2025-06-27 | House | 1 |  |  |  |  | 1 |  |  | State
Geraldine Road & Featherston Cres | Otara | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-30 | 2023-08-04 | 2024-04-11 | 2025-02-18 | House | 9 |  |  |  | 2 | 4 | 3 |  | State | 9033914.59
Geraldine Road & Featherston Cres | Otara | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-30 | 2023-08-04 | 2024-04-11 | 2025-02-18 | Terrace | 4 |  |  | 4 |  |  |  |  | State
Puroto Street | Meadowbank | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-02 | 2023-03-17 | 2023-07-24 | 2024-11-29 | Walk-up | 9 |  |  | 6 | 3 |  |  |  | State | 9052637.9
Matthew Place | Kawaha Point | Rotorua District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-03-04 | 2024-05-14 | 2024-09-16 | 2025-06-13 | Mixed | 19 |  | 10 | 8 | 1 |  |  |  | State | 9667139
Richardson Road | Mt Roskill | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2018-05-08 | 2020-10-29 |  | 2026-06-30 | Walk-up | 11 |  | 11 | [5 empty] | State | 9692911.01
Richardson Road | Mt Roskill | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2018-05-08 | 2020-10-29 |  | 2026-06-30 | Walk-up | 12 |  | 9 | 3 |  |  |  |  | State | 9692911.01
Fowlds Avenue | Sandringham | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-12-09 | 2023-03-30 | 2022-09-12 | 2025-06-30 | Walk-up | 15 |  | 9 | 6 |  |  |  |  | State | 9963363
Healy Road & Watts Road | Manurewa | Auckland | Contracted/Construction | Contracted | Redevelopment | Yes | Yes | 2024-08-08 | 2024-09-27 | 2024-10-07 | 2025-06-06 | Mixed | 17 |  | 3 | 2 | 8 | 2 | 2 |  | State | 10134600
Namata Road | Onehunga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-13 | 2023-08-25 | 2023-08-21 | 2024-12-17 | Duplex | 2 | [5 empty] | 2 |  | State | 10142207.94
Namata Road | Onehunga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-13 | 2023-08-25 | 2023-08-21 | 2024-12-17 | House | 4 |  |  |  | 1 |  | 3 |  | State
Namata Road | Onehunga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-13 | 2023-08-25 | 2023-08-21 | 2024-12-17 | Terrace | 6 |  |  | 6 |  |  |  |  | State
Balneavis Pl & Brabant Street | Opotiki | Opotiki District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-18 | 2024-07-29 |  | 2025-06-05 | House | 14 |  |  | 11 | 2 | 1 |  |  | State | 10728159
Balneavis Pl & Brabant Street | Opotiki | Opotiki District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-18 | 2024-07-29 |  | 2025-06-05 | House | 3 |  |  |  | 2 | 1 |  |  | State
Daventry Street | Waterview | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-16 | 2024-04-09 | 2024-04-09 | 2025-02-28 | Duplex | 6 |  |  | 4 | 2 |  |  |  | State | 12205607.72
Daventry Street | Waterview | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-16 | 2024-04-09 | 2024-04-09 | 2025-02-28 | House | 2 |  |  |  |  | 2 |  |  | State
Daventry Street | Waterview | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-16 | 2024-04-09 | 2024-04-09 | 2025-02-28 | Terrace | 10 |  |  | 7 |  | 3 |  |  | State
Beatty Place & Hood Street | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-10 | 2024-04-30 | 2024-06-04 | 2024-12-11 | House | 6 |  |  |  |  | 5 | 1 |  | State | 12557441.27
Beatty Place & Hood Street | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-10 | 2024-04-30 | 2024-06-04 | 2024-12-11 | House | 1 |  |  |  |  | 1 |  |  | State
Beatty Place & Hood Street | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-10 | 2024-04-30 | 2024-06-04 | 2025-02-10 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Beatty Place & Hood Street | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-10 | 2024-04-30 | 2024-06-04 | 2025-02-10 | House | 2 |  |  |  | 1 | 1 |  |  | State
Beatty Place & Hood Street | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-10 | 2024-04-30 | 2024-06-04 | 2025-06-19 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Beatty Place & Hood Street | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-08-10 | 2024-04-30 | 2024-06-04 | 2025-06-19 | House | 7 |  |  | 4 | 3 |  |  |  | State
Felix Street | Onehunga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-04-27 | 2023-08-22 | 2023-07-25 | 2025-01-30 | Apartment | 24 |  | 18 | 6 |  |  |  |  | State | 13069961.53
Balmoral Road & Townsend Pl | Whangarei | Whangarei District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-06-12 | 2024-08-27 | 2024-08-12 | 2025-06-27 | House | 20 |  |  |  | 16 | 2 | 2 |  | State | 13678661
Pearce Drive | Whangarei | Whangarei District | Contracted/Construction | Construction | Redevelopment | Yes | Yes |  |  | 2024-08-19 | 2025-05-27 | House | 20 |  | 2 | 10 | 4 | 4 |  |  | State | 13901154.03
Sussex Street & Grove Rd | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-30 | 2023-09-04 | 2024-05-02 | 2025-03-13 | Duplex | 8 |  |  | 8 |  |  |  |  | State | 14096372.92
Sussex Street & Grove Rd | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-30 | 2023-09-04 | 2024-05-02 | 2025-04-09 | House | 6 |  |  |  | 2 | 3 | 1 |  | State
Sussex Street & Grove Rd | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-30 | 2023-09-04 | 2024-05-02 | 2025-06-06 | Duplex | 6 |  |  | 6 |  |  |  |  | State
Sussex Street & Grove Rd | Hastings | Hastings District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-30 | 2023-09-04 | 2024-05-02 | 2025-06-06 | House | 4 |  |  | 2 | 1 | 1 |  |  | State
Triton Avenue & Tyburnia Avenue | Owairaka | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-15 | 2024-03-28 | 2024-08-19 | 2025-01-31 | Walk-up | 6 |  |  | 6 |  |  |  |  | Transitional | 14818326
Triton Avenue & Tyburnia Avenue | Owairaka | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-15 | 2024-03-28 | 2024-08-19 | 2025-01-31 | Walk-up | 18 |  | 6 | 12 |  |  |  |  | Transitional
Oranga Avenue & Houpara Street | Onehunga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-08-26 | 2021-12-21 | 2022-09-19 | 2024-11-29 | Duplex | 2 |  |  |  | 2 |  |  |  | State | 15528525.08
Leaver Pl & Mahia Rd, Weymouth | Weymouth | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-07 | 2023-06-15 | 2023-08-07 | 2024-11-21 | Duplex | 22 |  |  | 6 | 8 | 8 |  |  | State | 15679305.8
Leaver Pl & Mahia Rd, Weymouth | Weymouth | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-07 | 2023-06-15 | 2023-08-07 | 2024-11-21 | House | 3 |  |  |  | 1 | 1 | 1 |  | State | 15679305.8
Gladstone Road & Mill Road | Gisborne | Gisborne District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-01-25 | 2022-11-30 | 2023-07-18 | 2025-03-28 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State | 15985638.98
Gladstone Road & Mill Road | Gisborne | Gisborne District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-01-25 | 2022-11-30 | 2023-07-18 | 2025-06-13 | Walk-up | 9 |  |  | 9 |  |  |  |  | State | 15985638.98
Everitt Road, Cooper Cres & Ross Avenue | Otara | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-06-19 | 2023-11-23 | 2024-01-24 | 2024-10-21 | Duplex | 8 |  |  |  | 8 |  |  |  | State | 16262273.04
Everitt Road, Cooper Cres & Ross Avenue | Otara | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-06-19 | 2023-11-23 | 2024-01-24 | 2024-10-21 | House | 14 |  |  |  |  | 14 |  |  | State | 16262273.04
Reynolds Street & Taita Drive | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-06 | 2023-08-22 | 2023-07-24 | 2024-10-31 | Duplex | 4 |  |  |  | 2 |  | 2 |  | State | 16641169.95
Reynolds Street & Taita Drive | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-06 | 2023-08-22 | 2023-07-24 | 2024-10-31 | House | 1 |  |  |  |  | 1 |  |  | State
Reynolds Street & Taita Drive | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-06 | 2023-08-22 | 2023-07-24 | 2025-01-20 | Duplex | 6 |  |  |  | 4 |  | 2 |  | State
Reynolds Street & Taita Drive | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-06 | 2023-08-22 | 2023-07-24 | 2025-01-20 | House | 3 |  |  |  |  | 2 | 1 |  | State
Reynolds Street & Taita Drive | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-06 | 2023-08-22 | 2023-07-24 | 2025-01-20 | Terrace | 4 |  |  | 4 |  |  |  |  | State
Victoria Ave & Seddon St | Pukekohe | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-03-03 | 2022-07-08 | 2023-07-10 | 2025-01-31 | Apartment | 25 |  | 5 | 15 | 5 |  |  |  | State | 17914814.37
Edmonton Avenue | Onehunga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-17 | 2023-09-07 | 2023-03-06 | 2024-12-13 | Walk-up | 9 |  | 1 | 8 |  |  |  |  | State | 20460044.01
Edmonton Avenue | Onehunga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-17 | 2023-09-07 | 2023-03-06 | 2024-12-13 | Walk-up | 20 |  |  | 20 |  |  |  |  | State
Donegal Street | Avondale | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-29 | 2023-03-02 | 2023-05-01 | 2025-04-30 | Apartment | 21 |  | 1 | 20 |  |  |  |  | State | 23111574.31
Donegal Street | Avondale | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-29 | 2023-03-02 | 2023-05-01 | 2025-04-30 | Terrace | 4 |  |  | 2 | 2 |  |  |  | State
Donegal Street | Avondale | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-09-29 | 2023-03-02 | 2023-05-01 | 2025-04-30 | Walk-up | 6 |  |  |  | 6 |  |  |  | State
William Blofield Avenue & Sandringham Road | Wesley | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-02-16 | 2024-06-17 | 2023-06-01 | 2025-02-05 | Apartment | 20 |  |  | 10 | 10 |  |  |  | State | 24856466.77
William Blofield Avenue & Sandringham Road | Wesley | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-02-16 | 2024-06-17 | 2023-06-01 | 2025-02-28 | Walk-up | 11 |  |  | 6 | 5 |  |  |  | State | 24856466.77
Ranolf Street | Glenholme | Rotorua District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-12-13 | 2022-03-15 | 2022-02-14 | 2024-11-29 | Duplex | 12 |  | 12 | [5 empty] | State | 25777248
Greenslade Cres | Northcote | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-12-10 | 2023-11-16 | 2024-04-23 | 2025-06-30 | Apartment | 52 |  | 52 | [5 empty] | State | 26185700.23
Cadness Street | Northcote | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-06-29 | 2023-06-01 | 2022-12-19 | 2025-04-30 | Apartment | 56 |  | 33 | 14 | 9 |  |  |  | State | 34774065.91
Great North Road & Cadman Avenue | Waterview | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-09 | 2023-07-10 | 2023-07-17 | 2025-05-30 | Duplex | 4 |  |  |  |  | 2 | 2 |  | State | 36448104.37
Great North Road & Cadman Avenue | Waterview | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-09 | 2023-07-10 | 2023-07-17 | 2025-05-30 | House | 1 |  |  |  |  | 1 |  |  | State
Great North Road & Cadman Avenue | Waterview | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-09 | 2023-07-10 | 2023-07-17 | 2025-05-30 | Walk-up | 35 |  | 12 | 2 | 21 |  |  |  | State
Epuni Stage 3 | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2019-10-16 | 2021-09-20 | 2021-11-21 | 2024-10-31 | Walk-up | 36 |  | 24 | 12 |  |  |  |  | State | 66877161.28
Highbury Triangle (Great North Road) | Avondale | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2020-10-13 | 2022-04-20 | 2022-03-28 | 2025-02-21 | Apartment | 30 |  | 20 | 10 |  |  |  |  | State | 173495858
Renton Rd | Mt Albert | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-13 | 2022-10-19 | 2023-10-24 | 2024-10-31 | Duplex | 2 | 0 | 0 | 0 | 0 | 2 | 0 |  | State | 8953477.21
Renton Rd | Mt Albert | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-13 | 2022-10-19 | 2023-10-24 | 2024-10-31 | House | 1 | 0 | 0 | 0 | 1 | 0 | 0 |  | State
Renton Rd | Mt Albert | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-13 | 2022-10-19 | 2023-10-24 | 2025-02-14 | House | 1 | 0 | 0 | 0 | 1 | 0 | 0 |  | State
Renton Rd | Mt Albert | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-13 | 2022-10-19 | 2023-10-24 | 2024-10-31 | Terrace | 3 | 0 | 0 | 3 | 0 | 0 | 0 |  | State
Fenchurch Street | Redwood | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-11 | 2023-08-25 | 2024-03-25 | 2024-10-08 | Mixed | 9 |  | 6 | 2 | 1 |  |  |  | State
Watchfield Close | Mangere | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-05-18 | 2023-03-15 | 2023-03-15 | 2024-10-09 | Walk-up | 18 |  |  | 12 | 6 |  |  |  | State
Mayflower Close & Henwood Road | Mangere | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-08-20 | 2023-06-07 | 2024-04-19 | 2024-11-21 | Duplex | 4 |  |  | 2 |  |  | 2 |  | State
Atkinson Avenue | Otahuhu | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-11-05 | 2023-01-27 | 2023-04-04 | 2024-10-03 | Walk-up | 6 |  | 6 | [5 empty] | State
Atkinson Avenue | Otahuhu | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-11-05 | 2023-01-27 | 2023-04-04 | 2024-10-03 | Walk-up | 12 |  | 12 | [5 empty] | State
Hinemoa Street | Spreydon | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-13 | 2023-04-12 | 2023-12-13 | 2024-10-10 | House | 1 |  |  |  |  | 1 |  |  | State
Hinemoa Street | Spreydon | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-13 | 2023-04-12 | 2023-12-13 | 2024-10-10 | House | 2 |  |  |  |  | 2 |  |  | State
Chilcott Road | Henderson | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-04 | 2023-09-27 | 2023-09-25 | 2024-10-03 | House | 3 |  |  |  |  | 3 |  |  | State
Strathmore Ave | Wellington | Wellington City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-20 | 2024-02-28 | 2024-03-06 | 2024-10-18 | Duplex | 8 |  |  | 6 |  | 2 |  |  | State
Ruapehu Street | Paraparaumu | Kapiti Coast District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-07 | 2024-01-24 | 2024-01-24 | 2024-10-15 | House | 2 |  |  | 1 |  | 1 |  |  | State
St John Street | Opotiki | Opotiki District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-09 | 2023-09-07 | 2024-01-18 | 2024-10-31 | House | 3 |  |  |  |  | 2 | 1 |  | State
Harper St & Liddy Pl | Papakura | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-09 | 2023-05-29 | 2023-06-02 | 2024-10-31 | Duplex | 10 |  |  |  | 8 | 2 |  |  | State
Harper St & Liddy Pl | Papakura | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-09 | 2023-05-29 | 2023-06-02 | 2024-10-31 | House | 3 | [5 empty] | 3 |  | State
Green Street | Mosgiel | Dunedin City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-01-30 | 2023-04-14 | 2024-03-11 | 2024-11-01 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Princess Place & Williams Street | Kaiapoi | Waimakariri District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-31 | 2023-08-21 | 2023-12-11 | 2024-10-31 | Duplex | 10 |  |  | 10 |  |  |  |  | State
Princess Place & Williams Street | Kaiapoi | Waimakariri District | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-31 | 2023-08-21 | 2023-12-11 | 2024-10-31 | House | 4 |  |  |  | 1 | 1 | 2 |  | State
Cardiff Road & Opal Avenue | Pakuranga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-12 | 2023-05-05 | 2023-11-28 | 2024-10-08 | House | 1 | [6 empty] | 1 | State
Cardiff Road & Opal Avenue | Pakuranga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-12 | 2023-05-05 | 2023-11-28 | 2024-10-08 | House | 2 | [5 empty] | 1 | 1 | State
Cardiff Road & Opal Avenue | Pakuranga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-12 | 2023-05-05 | 2023-11-28 | 2024-10-08 | Terrace | 3 |  |  | 3 |  |  |  |  | State
Cardiff Road & Opal Avenue | Pakuranga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-12 | 2023-05-05 | 2023-11-28 | 2024-10-08 | Terrace | 3 |  |  | 3 |  |  |  |  | State
Cardiff Road & Opal Avenue | Pakuranga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-12 | 2023-05-05 | 2023-11-28 | 2024-10-31 | Duplex | 2 |  |  | 1 | 1 |  |  |  | State
Cardiff Road & Opal Avenue | Pakuranga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2022-12-12 | 2023-05-05 | 2023-11-28 | 2024-10-31 | House | 1 | [6 empty] | 1 | State
Bader Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-05 | 2023-11-16 | 2023-11-02 | 2024-10-29 | Duplex | 2 |  |  | 2 |  |  |  |  | State
Bader Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-07-05 | 2023-11-16 | 2023-11-02 | 2024-10-29 | House | 3 |  |  |  | 3 |  |  |  | State
Holcombe Place & Studholme Street | Somerfield | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-04 | 2023-06-28 | 2024-02-12 | 2024-10-10 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Holcombe Place & Studholme Street | Somerfield | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-04 | 2023-06-28 | 2024-02-12 | 2024-10-10 | House | 2 |  |  | 2 |  |  |  |  | State
Lumsden Road | Hastings | Hastings District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2025-06-30 | 2025-06-30 | House | 1 |  |  |  | 1 |  |  |  | State
Breckons Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-08 | 2023-09-06 | 2023-10-24 | 2024-11-15 | Terrace | 7 |  |  | 7 |  |  |  |  | State
Athlone Crescent | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-03-13 | 2023-12-15 | 2024-05-09 | 2024-10-10 | House | 2 |  |  | 2 |  |  |  |  | State
Primrose Street | Northcote | Christchurch City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-05-12 | 2023-12-04 | 2024-03-25 | 2024-10-07 | Mixed | 9 | 3 | 6 | [5 empty] | State
Exeter Cres | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  | 2024-10-16 | 2025-04-04 | House | 2 |  |  | 1 | 1 |  |  |  | State
Gosport Place | Onehunga | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-04-28 | 2023-10-20 | 2024-03-11 | 2024-10-29 | House | 4 |  |  |  | 3 | 1 |  |  | State
Cottrell Place & Moncreiff Avenue | Manurewa | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-10-27 | 2023-12-20 | 2024-03-25 | 2024-10-23 | Mixed | 6 |  | 2 |  | 2 |  | 2 |  | State
Selwyn Street | Invercargill | Invercargill City | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2024-02-28 | 2024-03-04 | 2024-06-12 | 2024-11-01 | House | 3 |  | 3 | [5 empty] | State
Alford Street | Waterview | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-02-23 | 2024-02-01 | 2024-03-04 | 2024-10-10 | Mixed | 3 |  |  |  |  | 2 | 1 |  | State
Mahia Road | Manurewa | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2023-12-06 | 2023-12-15 | 2024-01-22 | 2024-10-11 | Mixed | 9 |  | 2 | 3 | 4 |  |  |  | State
Orchard Street | Avondale | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes |  | 2024-03-06 | 2024-07-08 | 2024-10-16 | House | 1 |  |  | 1 |  |  |  |  | State
Mayflower Close & Henwood Road | Mangere | Auckland | Contracted/Construction | Construction | Redevelopment | Yes | Yes | 2021-08-20 | 2023-06-07 | 2024-04-19 | 2024-11-21 | House | 7 |  |  |  | 3 | 2 | 1 | 1 | State
Dalrymple Road | Gisborne | Gisborne District | Contracted/Construction | Contracted | Acquired new | Yes | Yes |  |  |  | 2025-12-18 | Duplex, House, Terrace | 32 |  |  | 19 |  | 13 |  |  | State
North Street | Palmerston North | Palmerston North City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2022-07-18 | 2023-06-07 | 2022-08-15 | 2024-11-28 | Terrace, Walk-up | 50 |  |  | 33 | 14 | 3 |  |  | State
Black Street | Wairoa | Wairoa District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2023-02-09 |  |  | 2025-05-01 | Duplex, House | 7 |  |  | 2 | 4 |  |  | 1 | State
Black Street | Wairoa | Wairoa District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2023-02-09 |  |  | 2025-06-03 | House | 3 |  |  |  | 1 | 2 |  |  | State
Black Street | Wairoa | Wairoa District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2023-02-09 |  |  | 2025-07-21 | Duplex, House | 7 |  |  | 6 |  | 1 |  |  | State
Black Street | Wairoa | Wairoa District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2023-02-09 |  |  | 2025-08-21 | Duplex, House | 6 |  |  | 2 | 4 |  |  |  | State
Black Street | Wairoa | Wairoa District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2023-02-09 |  |  | 2025-09-09 | House | 2 |  |  |  | 2 |  |  |  | State
Black Street | Wairoa | Wairoa District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2023-02-09 |  |  | 2026-02-17 | Duplex, House | 5 |  |  | 2 |  | 3 |  |  | State
Vine Street | Mangere | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2021-12-21 | 2022-10-28 | 2024-07-03 | 2025-05-20 | House | 6 |  |  |  |  | 2 | 4 |  | State
Wanaka Street | Whangarei | Whangarei District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2022-08-31 | 2023-08-23 | 2023-07-24 | 2024-10-17 | Apartment | 55 |  | 12 | 39 | 4 |  |  |  | State
Glenview Road | Glen Eden | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2022-10-27 | 2023-09-07 | 2023-10-30 | 2024-11-20 | Walk-up | 24 |  |  | 15 | 9 |  |  |  | State
Domain Terrace | Spreydon | Christchurch City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-05-02 | 2023-12-12 | 2023-12-12 | 2024-12-06 | Duplex, House, Terrace | 24 |  | 6 | 15 | 1 | 1 | 1 |  | State
Royton Avenue & Yates Road | Mangere | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-02-21 | 2023-08-08 | 2023-10-05 | 2024-11-08 | Terrace | 13 |  |  |  | 13 |  |  |  | State
Waimea Road | Nelson | Nelson City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-04-17 | 2023-08-15 | 2023-10-20 | 2025-01-30 | Walk-up | 29 |  | 29 | [5 empty] | State
Ballance Place | Napier | Napier City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-01-26 | 2024-06-18 | 2024-06-18 | 2025-02-20 | House | 6 |  |  | 6 |  |  |  |  | State
Mansfield Road | Rotorua | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-09-27 |  | 2024-08-12 | 2025-08-01 | Duplex, House | 49 |  | 6 | 4 | 12 | 21 | 3 | 3 | State
Clevedon Road | Papakura | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-02-24 | 2023-09-20 | 2023-11-01 | 2025-02-13 | Walk-up | 18 |  |  | 10 | 8 |  |  |  | State
Neale Avenue | Nelson | Nelson City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-01-19 | 2024-09-13 | 2024-09-02 | 2025-06-06 | Duplex, Terrace | 26 |  | 8 | 14 | 4 |  |  |  | State
Lake Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-03-13 | 2024-03-13 | 2024-06-10 | 2025-04-11 | Duplex, Terrace | 13 |  |  | 13 |  |  |  |  | State
Saxbys Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-23 |  | 2024-04-22 | 2024-11-20 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Bordesley Street | Phillipstown | Christchurch City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2022-11-16 | 2023-10-13 | 2023-12-07 | 2025-06-16 | House, Terrace | 16 |  |  | 16 |  |  |  |  | State
Alexander Crescent | Otara | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-02-13 | 2023-08-14 | 2023-10-04 | 2024-11-28 | Duplex, Terrace | 57 |  |  | 39 | 14 | 4 |  |  | State
Racecourse Road | Waipukurau | Central Hawke's Bay District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-02-10 | 2023-12-06 | 2023-12-07 | 2024-10-30 | Duplex, House | 12 |  |  | 6 | 6 |  |  |  | State
Kauika Road | Whangarei | Whangarei District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2022-11-02 | 2024-03-14 | 2024-06-18 | 2025-05-15 | House, Walk-up | 27 |  |  | 24 | 1 | 2 |  |  | State
Kauika Road | Whangarei | Whangarei District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2022-11-02 | 2024-03-14 | 2024-08-05 | 2026-03-19 | Walk-up | 44 |  | 15 | 29 |  |  |  |  | State
Kauika Road | Whangarei | Whangarei District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2022-11-02 | 2024-03-14 | 2024-08-01 | 2026-06-02 | House, Walk-up | 24 |  | 6 | 15 | 2 | 1 |  |  | State
Steele Road | Gisborne | Gisborne District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-05 | 2024-04-09 | 2024-07-16 | 2025-09-01 | House | 11 |  |  | 9 | 2 |  |  |  | State
Victoria Street | Rotorua | Rotorua District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-05-22 |  |  | 2026-03-26 | Walk-up | 36 |  | 21 | 15 |  |  |  |  | State
Rimu Street | Hastings | Hastings District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-23 | 2024-02-14 | 2024-02-28 | 2025-04-25 | Duplex | 10 |  |  | 10 |  |  |  |  | State
Fitzherbert Street | Featherston | South Wairarapa District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2023-01-24 |  |  | 2025-05-20 | Walk-up | 11 |  | 2 | 9 |  |  |  |  | State
Barton Avenue | Napier | Napier City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-21 | 2024-06-14 | 2024-06-14 | 2025-09-25 | Duplex, Terrace, Walk-up | 30 |  | 1 | 23 | 6 |  |  |  | State
Shakespeare Street | Greymouth | Grey District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-04-17 |  |  | 2025-06-13 | House | 5 |  |  | 5 |  |  |  |  | State
Roebuck Road | Gisborne | Gisborne District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-03-27 | 2023-08-23 | 2023-11-20 | 2025-01-29 | Walk-up | 10 |  |  | 8 | 2 |  |  |  | State
Rosebank Road | Avondale | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-10-13 | 2024-05-22 | 2024-06-04 | 2025-05-20 | Terrace | 32 |  |  | 9 | 23 |  |  |  | State
High Street | Greymouth | Grey District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-02-01 |  |  | 2025-06-13 | House | 4 |  |  | 4 |  |  |  |  | State
Main Road South | Raumati | Porirua City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-08-22 | 2024-08-23 | 2024-07-10 | 2025-07-30 | Duplex, House, Terrace | 26 |  |  | 15 | 11 |  |  |  | State
McKenzie Road | Mangere Bridge | Auckland | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-07-19 |  |  | 2026-03-19 | Terrace, Walk-up | 43 |  |  | 12 | 17 | 14 |  |  | State
Bush Street | Lower Hutt | Lower Hutt City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-05-10 | 2023-08-14 | 2024-02-19 | 2025-05-14 | Duplex, Terrace | 13 |  |  | 9 | 4 |  |  |  | State
Sturdee Road | Manurewa | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-21 | 2023-12-20 | 2024-06-04 | 2024-11-27 | Duplex, Terrace | 5 |  |  |  | 4 | 1 |  |  | State
Tawa Crescent | Manurewa | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-28 | 2024-01-18 | 2024-06-04 | 2025-01-30 | Duplex, Terrace | 7 |  |  | 2 | 5 |  |  |  | State
Manson Street | Gate Pa | Tauranga City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-08 | 2023-09-13 | 2023-11-08 | 2024-11-27 | Terrace | 19 |  |  | 19 |  |  |  |  | State
Wellesley Road | Napier | Napier City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-03-17 | 2023-11-14 | 2024-01-09 | 2025-02-13 | Apartment | 12 |  |  | 12 |  |  |  |  | State
Boucher Avenue | Te Puke | Western Bay of Plenty District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-29 | 2023-11-29 | 2024-01-08 | 2024-11-13 | Duplex, Terrace | 5 |  |  | 5 |  |  |  |  | State
Dampier Street | Avondale | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-05-12 | 2023-10-10 | 2024-06-03 | 2024-12-16 | Duplex, House | 3 |  |  |  |  | 3 |  |  | State
Chadwick Road | Greerton | Tauranga City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-21 | 2023-09-22 | 2023-12-08 | 2024-11-19 | Duplex, Terrace | 12 |  |  | 12 |  |  |  |  | State
Fitzherbert Street | Hokitika | Westland District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2022-04-19 |  |  | 2025-06-06 | House | 2 |  |  | 2 |  |  |  |  | State
Clayton Road | Mangakakahi | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-09-28 | 2024-01-18 | 2024-03-08 | 2024-11-15 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Reeves Road | Pakuranga | Auckland | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2023-10-20 | 2023-12-19 |  | 2025-07-31 | Terrace | 12 |  |  | 7 | 2 | 3 |  |  | State
School Road | Gisborne | Gisborne District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-28 | 2023-10-04 | 2024-04-01 | 2025-02-27 | Duplex | 4 |  |  |  |  | 4 |  |  | State
Skipton Street | Mangere | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-03-13 | 2024-07-03 | 2024-09-10 | 2025-05-23 | House | 7 |  |  |  | 1 | 6 |  |  | State
Island View Road | Western Height | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-09-28 | 2024-01-17 | 2024-03-04 | 2024-11-15 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Gladstone Road | Gisborne | Gisborne District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-01-25 | 2024-06-04 | 2024-06-18 | 2025-05-28 | Terrace, Walk-up | 15 |  |  | 15 |  |  |  |  | State
Kelvin Road | Remuera | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-01 | 2023-11-15 | 2024-07-22 | 2025-07-18 | Terrace | 24 |  |  | 12 |  | 12 |  |  | State
Worksop Road | Masterton | Masterton District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-10-10 | 2024-01-11 | 2024-04-23 | 2024-12-17 | Duplex, House | 12 |  |  | 10 | 2 |  |  |  | State
Hood Avenue | Upper Hutt | Upper Hutt City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-05-17 | 2023-09-08 | 2024-02-26 | 2025-05-01 | Duplex, House | 5 |  |  |  |  | 5 |  |  | State
Fairy Springs Road | Fairy Springs | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-12-15 | 2024-02-01 | 2024-03-08 | 2024-12-10 | Terrace | 6 |  |  | 6 |  |  |  |  | State
Aldwins Road | Phillipstown | Christchurch City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-07-03 | 2023-10-20 | 2023-11-08 | 2025-02-28 | House, Terrace | 8 |  |  | 8 |  |  |  |  | State
Royal View Road | Te Atatu | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-04 | 2024-04-28 | 2024-05-14 | 2024-12-02 | Duplex, House | 6 |  |  | 6 |  |  |  |  | State
Fairy Springs Road | Fairy Springs | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-02-28 | 2024-09-26 | 2024-05-06 | 2025-05-14 | Duplex, Terrace | 10 |  |  | 8 | 2 |  |  |  | State
Killarney Road & Burrows Place | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-21 | 2024-01-16 | 2024-01-17 | 2024-10-25 | Terrace | 9 |  |  | 7 | 2 |  |  |  | State
Killarney Road & Burrows Place | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-21 | 2024-05-07 | 2024-05-01 | 2025-05-01 | Terrace, Walk-up | 12 |  | 2 | 10 |  |  |  |  | State
Killarney Road & Burrows Place | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-21 | 2024-06-24 | 2024-07-01 | 2025-05-01 | Terrace | 11 |  |  | 9 | 2 |  |  |  | State
Malfroy Road | Glenholme | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-03-01 | 2024-07-24 | 2024-09-16 | 2025-04-23 | Terrace | 6 |  |  | 6 |  |  |  |  | State
Doyle Street | Greymouth | Grey District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-06-07 |  |  | 2025-06-13 | Duplex, House | 8 |  |  | 8 |  |  |  |  | State
Southland Road | Hastings | Hastings District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-10-13 | 2024-01-19 | 2024-02-05 | 2025-01-30 | Duplex | 6 |  |  | 2 | 4 |  |  |  | State
Oxford Street | Richmond | Tasman District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-03-18 | 2024-05-29 | 2024-05-29 | 2024-12-13 | Duplex, House | 6 |  |  | 6 |  |  |  |  | State
Brookfield Terrace | Brookfield | Tauranga City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-06-25 | 2024-09-05 |  | 2025-05-08 | Terrace | 6 |  |  | 6 |  |  |  |  | State
Greta Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-30 | 2024-06-20 | 2024-05-20 | 2024-12-17 | Duplex | 4 |  |  | 1 | 3 |  |  |  | State
Taranaki Street | Wellington | Wellington City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2022-07-07 | 2023-01-12 | 2023-11-01 | 2024-11-28 | Apartment | 36 |  | 33 | 3 |  |  |  |  | State
Travis Road | Burwood | Christchurch City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-30 | 2024-01-12 | 2024-03-04 | 2024-11-28 | House | 5 |  |  |  | 5 |  |  |  | State
Albert Street | Palmerston North | Palmerston North City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-18 | 2023-08-28 | 2023-11-01 | 2024-10-17 | Duplex, House, Terrace | 12 |  |  | 12 |  |  |  |  | State
Maich Road | Manurewa | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-30 | 2024-01-16 | 2024-04-01 | 2025-04-25 | Terrace | 15 |  |  | 4 | 7 | 3 |  | 1 | State
Clark Road | Kerikeri | Far North District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-06-14 | 2023-10-23 | 2023-10-30 | 2024-10-22 | Walk-up | 8 |  |  | 8 |  |  |  |  | State
Clark Road | Kerikeri | Far North District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-11 | 2024-06-04 | 2024-06-04 | 2025-05-15 | Terrace, Walk-up | 14 |  |  | 12 | 2 |  |  |  | State
Galbraith Street | Ngaruawahia | Waikato District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-27 |  | 2024-07-15 | 2025-03-21 | Duplex | 8 |  |  | 4 |  | 4 |  |  | State
Galbraith Street | Ngaruawahia | Waikato District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-27 |  | 2024-07-15 | 2025-06-03 | Duplex, Terrace | 12 |  |  | 4 | 8 |  |  |  | State
Avenue Road | Otahuhu | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-07-24 | 2024-05-08 | 2024-05-08 | 2025-04-17 | House | 6 |  |  | 6 |  |  |  |  | State
Margaret Street | Palmerston North | Palmerston North City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-05 | 2023-12-15 | 2024-01-18 | 2025-02-26 | Duplex, Terrace | 14 |  |  | 10 | 4 |  |  |  | State
Rangiamohia Road | Turangi | Taupo District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-07-31 | 2023-10-17 | 2024-02-23 | 2024-10-11 | Duplex, House | 7 |  |  | 6 | 1 |  |  |  | State
Makoura Road | Masterton | Masterton District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-10-03 | 2024-01-18 | 2024-06-17 | 2025-04-07 | Duplex, House | 12 |  |  | 9 | 3 |  |  |  | State
Lancaster Road | Beach Haven | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-09-12 | 2024-03-01 | 2023-11-20 | 2024-12-11 | House, Terrace | 12 |  |  | 9 |  | 3 |  |  | State
River Road | Kawerau | Kawerau District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-05 | 2024-09-05 | 2024-09-16 | 2025-04-23 | House | 3 |  |  |  | 3 |  |  |  | State
Owen Street | Feilding | Manawatu District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-09-29 | 2024-01-30 | 2024-03-04 | 2024-12-16 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Lisa Crescent | Mangakakahi | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-02-21 | 2024-02-21 | 2024-03-04 | 2025-09-01 | Duplex, Terrace | 5 |  |  | 3 | 2 |  |  |  | State
Cole Street | Dannevirke | Tararua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-09-22 | 2024-01-10 | 2024-05-20 | 2024-12-17 | Duplex, House | 7 |  |  | 7 |  |  |  |  | State
Alison Street | Mangakakahi | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-02-22 | 2024-02-22 | 2024-04-15 | 2024-11-06 | Duplex, House | 3 |  |  | 3 |  |  |  |  | State
Roosevelt Road | Western Heights | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-14 | 2023-11-24 | 2024-04-12 | 2025-02-19 | Terrace | 6 |  |  | 4 | 2 |  |  |  | State
Gossamer Drive | Pakuranga | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-12-08 | 2024-03-08 | 2024-05-01 | 2024-12-18 | Terrace | 13 |  |  | 4 | 3 | 5 | 1 |  | State
Goldsmith Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-07-03 | 2024-09-02 | 2024-07-01 | 2025-06-05 | Terrace | 5 |  |  | 3 | 2 |  |  |  | State
Wellington Road | Marton | Rangitikei District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-02-23 | 2024-07-17 | 2024-08-01 | 2025-05-06 | Duplex | 8 |  |  | 8 |  |  |  |  | State
Rawhiti Street | Greerton | Tauranga City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-12-08 | 2024-02-02 | 2024-05-06 | 2025-02-03 | Duplex, Terrace | 10 |  |  | 7 | 3 |  |  |  | State
Ranolf Street | Glenholme | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-24 | 2024-06-04 | 2024-07-01 | 2025-03-12 | House, Terrace | 5 |  |  | 3 | 1 | 1 |  |  | State
Heretaunga Street | Palmerston North | Palmerston North City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-15 | 2024-06-10 | 2024-06-06 | 2025-07-11 | Terrace | 3 |  |  | 3 |  |  |  |  | State
Baycroft Avenue | Parkvale | Tauranga City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-09-20 | 2023-11-09 | 2023-11-27 | 2024-11-20 | Terrace | 5 |  |  | 5 |  |  |  |  | State
Birkenhead Avenue | Birkenhead | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-03-13 | 2024-04-02 | 2024-07-22 | 2025-08-15 | Walk-up | 15 |  | 15 | [5 empty] | State
Totara Drive | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-01-16 | 2024-02-19 | 2024-03-13 | 2024-10-14 | Duplex, House | 3 |  |  | 1 | 1 | 1 |  |  | State
Kamo Road | Whangarei | Whangarei District | Contracted/Construction | Contracted | Acquired new | Yes | Yes |  |  |  | 2025-08-30 | Terrace, Walk-up | 7 |  |  | 5 | 2 |  |  |  | State
Kamo Road | Kaitaia | Whangarei District | Contracted/Construction | Contracted | Acquired new | Yes | Yes |  |  |  | 2026-02-18 | Terrace, Walk-up | 11 |  |  | 9 | 2 |  |  |  | State
Grigg Street | Kaitaia | Far North District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-11-19 | House | 5 |  |  | 1 | 3 |  | 1 |  | State
Grigg Street | Kaitaia | Far North District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-22 |  | 2024-05-06 | 2024-12-02 | House | 5 |  |  | 2 | 1 | 2 |  |  | State
Grigg Street | Kaitaia | Far North District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-22 |  | 2024-05-06 | 2025-02-12 | House | 7 |  |  |  | 3 | 3 | 1 |  | State
Gisborne Road | Te Puke | Western Bay of Plenty District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-12-20 | 2023-11-06 | 2024-04-05 | 2024-11-08 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Brookland Road | Western Heights | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-30 | 2024-05-24 | 2024-07-01 | 2025-02-26 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Kea Street | Selwyn Heights | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-24 |  | 2024-05-29 | 2025-03-18 | Duplex, House | 5 |  |  | 2 | 3 |  |  |  | State
Old Taupo Road | Hillcrest | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-03-20 | 2024-03-26 | 2024-05-17 | 2025-02-03 | Terrace | 5 |  |  | 3 | 2 |  |  |  | State
Boucher Avenue | Te Puke | Western Bay of Plenty District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-02-14 | 2024-03-27 | 2024-04-29 | 2025-07-01 | Duplex, Terrace | 11 |  |  | 11 |  |  |  |  | State
Norman Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-08-30 | 2024-01-24 | 2024-05-23 | 2025-02-21 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Mansel Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-07-24 | 2024-08-22 | 2024-05-31 | 2025-03-03 | House | 3 |  |  | 1 | 1 |  | 1 |  | State
Oxford Street | Palmerston North | Palmerston North City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-08-02 |  |  | 2025-08-06 | Duplex | 10 |  |  | 8 | 2 |  |  |  | State
Rifle Range Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-10-24 | 2024-03-19 | 2024-03-01 | 2024-11-15 | Terrace | 3 |  |  |  |  | 3 |  |  | State
Belvedere Street | Te Puke | Western Bay of Plenty District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-02-23 | 2024-02-08 | 2024-07-15 | 2025-03-20 | Duplex, Terrace | 6 |  |  | 4 | 2 |  |  |  | State
Ottawa Road | Wainoni | Christchurch City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-10-20 | 2023-12-13 | 2024-02-12 | 2024-11-14 | House | 5 |  | 5 | [5 empty] | State
Merivale Road | Parkvale | Tauranga City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-08 | 2024-02-14 | 2024-04-18 | 2024-11-13 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Fitzherbert Street | Hokitika | Westland District | Contracted/Construction | Construction | Acquired new | Yes | Yes |  | 2023-12-08 | 2024-02-19 | 2025-01-23 | Duplex, House | 9 |  |  | 9 |  |  |  |  | State
Ulster Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-01 | 2024-01-30 | 2024-03-13 | 2024-10-18 | Terrace | 6 |  |  | 4 | 2 |  |  |  | State
Ottawa Road | Wainoni | Christchurch City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-07-24 | 2024-01-15 | 2024-02-08 | 2024-11-22 | House | 5 |  | 5 | [5 empty] | State
Elizabeth Street | Taupo | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-02 | 2024-02-08 | 2024-04-01 | 2024-10-14 | Duplex | 4 |  |  | 4 |  |  |  |  | State
McKenzie Street | Levin | Horowhenua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-04-03 | 2024-01-31 | 2024-01-15 | 2025-03-03 | House | 16 |  | 16 | [5 empty] | State
Aberdeen Road | Gisborne | Gisborne District | Contracted/Construction | Contracted | Acquired new | Yes | Yes |  |  |  | 2026-04-20 | Duplex, House | 12 |  |  | 11 | 1 |  |  |  | State
Murdoch Crescent | Whangarei | Whangarei District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-05-05 | 2024-05-05 |  | 2025-07-30 | Terrace | 12 |  |  | 11 | 1 |  |  |  | State
Princess Road | Bellevue | Tauranga City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-02-09 | 2024-02-16 | 2024-06-24 | 2024-12-12 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Clayton Road | Mangakakahi | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-12-11 | 2024-03-01 | 2024-04-29 | 2025-02-19 | Duplex, Terrace | 5 |  |  | 1 | 2 | 2 |  |  | State
Frederick Street West | Hastings | Hastings District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-02-01 | 2024-03-21 | 2024-05-14 | 2025-02-27 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Dixon Avenue | Hawera | South Taranaki District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-05-28 | 2024-09-03 |  | 2025-07-17 | Duplex | 6 |  |  | 6 |  |  |  |  | State
Port Street East | Feilding | Manawatu District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-14 | 2024-06-17 | 2024-06-18 | 2026-05-08 | House | 20 |  |  | 5 | 11 | 4 |  |  | State
Stanley Road | Gisborne | Gisborne District | Contracted/Construction | Contracted | Acquired new | Yes | Yes |  |  |  | 2026-03-20 | Duplex | 8 |  |  | 6 | 2 |  |  |  | State
Clayton Road | Mangakakahi | Rotorua District | Contracted/Construction | Construction | Acquired new | Yes | Yes |  | 2024-07-01 | 2024-06-27 | 2025-01-30 | House | 3 |  |  | 1 | 2 |  |  |  | State
Finlayson Avenue | Clendon | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-01-31 | 2024-05-14 | 2024-07-22 | 2025-05-29 | Duplex, Terrace | 7 |  |  |  |  | 5 | 2 |  | State
Galloway Street | Dunedin | Dunedin City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-10 | 2024-04-12 | 2024-04-13 | 2024-12-05 | Terrace | 7 |  |  | 7 |  |  |  |  | State
Doon Street | Mosgiel | Dunedin City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-10-27 | 2024-06-05 | 2024-04-29 | 2025-03-11 | Duplex | 5 |  |  | 5 |  |  |  |  | State
Alexandra Street | Te Awamutu | Waipa District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-02-22 |  | 2024-05-20 | 2025-04-14 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Beach Road | New Brighton | Christchurch City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-12-13 | 2024-04-03 | 2024-04-15 | 2025-07-24 | Duplex, House | 8 |  |  | 8 |  |  |  |  | State
Taradale Road | Napier | Napier City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-05-21 | 2024-06-11 | 2024-06-21 | 2025-06-12 | Duplex, House | 7 |  |  | 7 |  |  |  |  | State
St Aubyn Street | New Plymouth | New Plymouth District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-05-14 |  |  | 2026-02-12 | Walk-up | 16 |  | 16 | [5 empty] | State
Liverpool Street | Levin | Horowhenua District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-04-22 | 2024-07-04 |  | 2025-09-02 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Mackworth Street | Woolston | Christchurch City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-03-19 | 2024-07-22 |  | 2025-07-01 | House | 5 |  | 5 | [5 empty] | State
Hukanui Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-03-25 | 2024-05-31 | 2024-04-22 | 2025-02-20 | Duplex | 4 |  |  | 2 |  | 2 |  |  | State
Nash Street | Napier | Napier City | Contracted/Construction | Contracted | Acquired new | Yes | Yes |  |  |  | 2025-10-17 | Duplex, House | 5 |  |  | 4 | 1 |  |  |  | State
Thomson Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-22 | 2024-06-25 | 2024-05-23 | 2025-03-25 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Queen Street West | Hastings | Hastings District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-17 | 2024-07-25 | 2024-07-31 | 2025-07-15 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Taradale Road | Napier | Napier City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-01-26 | 2024-07-18 | 2024-07-15 | 2025-08-05 | House | 10 |  |  |  | 5 | 5 |  |  | State
McAnnalley Street | Manurewa | Auckland | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-10 | 2024-07-04 | 2024-08-21 | 2025-05-30 | House | 4 |  |  |  |  | 4 |  |  | State
Greta Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-30 | 2024-07-15 | 2024-05-20 | 2025-07-01 | Duplex | 4 |  |  | 2 |  | 2 |  |  | State
Dawson Street | New Plymouth | New Plymouth District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-24 | 2024-09-16 | 2024-06-03 | 2025-11-04 | Walk-up | 14 |  | 14 | [5 empty] | State
Warwick Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-22 | 2024-04-08 | 2024-05-01 | 2024-11-26 | Duplex | 4 |  |  |  |  | 4 |  |  | State
Mahana Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-03-06 | 2024-03-27 | 2024-03-27 | 2024-12-02 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Snelson Street | Palmerston North | Palmerston North City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-05-24 |  |  | 2025-06-03 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Totara Drive | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-01-24 | 2024-05-07 | 2024-05-13 | 2024-12-17 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Main South Road | Hornby | Christchurch City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-05 | 2024-07-22 | 2024-08-12 | 2025-07-08 | House | 8 |  | 7 | 1 |  |  |  |  | State
Argyll Road & Stirling Grove | Greerton | Tauranga City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-03-26 |  |  | 2025-10-09 | House, Terrace | 12 |  |  | 6 | 3 | 3 |  |  | State
Warwick Road | Hastings | Hastings District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-18 | 2024-07-25 | 2024-07-25 | 2025-07-23 | House | 5 |  |  | 1 | 3 | 1 |  |  | State
River Road | Masterton | Masterton District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-07-04 | 2024-07-05 | 2024-07-04 | 2025-06-11 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Mears Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-04-17 | 2024-07-02 | 2024-06-03 | 2025-04-01 | Duplex, House | 6 |  |  | 2 | 2 | 2 |  |  | State
McKenzie Street | Levin | Horowhenua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-12-08 | 2024-01-31 | 2024-05-31 | 2025-03-03 | House | 2 |  |  | 2 |  |  |  |  | State
Scannell Street | Taupo | Taupo District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-05 | 2024-08-22 | 2024-09-13 | 2025-09-01 | Duplex, House | 10 |  |  | 7 | 3 |  |  |  | State
Queen Road | Bellevue | Tauranga City | Contracted/Construction | Contracted | Acquired new | Yes | Yes |  |  |  | 2025-10-31 | Duplex, House | 5 |  |  | 4 | 1 |  |  |  | State
Irvine Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-03-06 | 2024-04-25 | 2024-05-03 | 2024-12-05 | Duplex | 4 |  |  |  |  | 4 |  |  | State
Potaka Street | Marton | Rangitikei District | Contracted/Construction | Construction | Acquired new | Yes | Yes |  | 2024-06-18 | 2024-07-22 | 2025-05-06 | House | 2 |  |  |  | 2 |  |  |  | State
Maitland Street | Dunedin | Dunedin City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2021-10-07 | 2023-12-05 | 2024-07-01 | 2025-06-05 | Terrace | 7 |  | 6 | 1 |  |  |  |  | State
Kamo Road | Whangarei | Whangarei District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-08-09 |  |  | 2025-06-04 | Terrace | 6 |  | 6 | [5 empty] | State
Tasman Street | Greymouth | Grey District | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-07-09 |  |  | 2025-10-30 | Duplex, House | 8 |  |  | 7 | 1 |  |  |  | State
Whatawhata Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-06-12 | 2024-07-01 | 2024-07-01 | 2025-04-01 | Duplex | 2 |  |  |  |  | 2 |  |  | State
Highland Drive | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-07-22 | 2024-08-28 | 2024-07-22 | 2025-03-03 | Duplex | 6 |  |  | 2 | 2 | 2 |  |  | State
Masons Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-07-24 | 2024-09-30 | 2024-07-29 | 2025-05-30 | Terrace | 8 |  | 8 | [5 empty] | State
Fuchsia Avenue | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-07-04 | 2024-09-25 | 2024-07-15 | 2025-05-30 | Duplex, House | 6 |  |  | 1 | 3 | 2 |  |  | State
Vardon Road | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-08-08 | 2024-08-07 | 2024-08-01 | 2025-04-14 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Church Road | Hamilton | Hamilton City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-08-01 |  |  | 2025-05-01 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Trafalgar Street | Levin | Horowhenua District | Contracted/Construction | Construction | Acquired new | Yes | Yes |  | 2022-03-15 | 2024-07-19 | 2024-12-11 | House | 1 |  |  |  |  | 1 |  |  | State
Larnach Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-07-25 | 2024-08-13 | 2024-08-05 | 2025-05-28 | Duplex, House | 3 |  |  | 2 |  | 1 |  |  | State
Rimu Street | Hamilton | Hamilton City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-08-23 |  |  | 2025-06-05 | Terrace | 4 |  |  |  | 4 |  |  |  | State
Linton Street | Palmerston North | Palmerston North City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-05-09 | 2024-06-14 | 2024-07-15 | 2025-04-09 | Duplex, Terrace | 7 |  |  | 7 |  |  |  |  | State
Comries Road | Hamilton | Hamilton City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-08-19 | 2024-08-29 |  | 2025-05-28 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Trafalgar Street | Levin | Horowhenua District | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2022-01-06 | 2023-02-28 | 2024-07-19 | 2024-12-05 | House | 1 |  |  |  | 1 |  |  |  | State
Forsyth Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-08-08 | 2024-08-08 | 2024-07-29 | 2025-06-01 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Heath Street | Hamilton | Hamilton City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2024-08-13 | 2024-08-19 | 2024-09-01 | 2025-05-28 | Duplex | 8 |  |  | 8 |  |  |  |  | State
Belvedere Crescent | Palmerston North | Palmerston North City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-06-05 |  |  | 2025-04-09 | House | 1 |  |  |  |  | 1 |  |  | State
Paisley Street | Palmerston North | Palmerston North City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2018-11-13 | 2024-06-20 | 2024-08-26 | 2025-03-14 | House | 1 |  |  |  |  | 1 |  |  | State
Geddis Avenue | Napier | Napier City | Contracted/Construction | Contracted | Acquired new | Yes | Yes |  |  |  | 2025-06-05 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Mangakahia Road | Kaikohe | Far North District | Contracted/Construction | Contracted | Acquired new | Yes | Yes |  |  |  | 2025-05-29 | House | 13 |  |  | 4 | 9 |  |  |  | State
Tanekaha Place | Hamilton | Hamilton City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-08-05 | 2024-08-20 |  | 2025-05-28 | Duplex | 6 |  |  | 4 | 2 |  |  |  | State
Morrow Avenue | Hamilton | Hamilton City | Contracted/Construction | Contracted | Acquired new | Yes | Yes | 2024-08-21 |  |  | 2025-06-03 | Duplex | 6 |  |  | 2 | 2 | 2 |  |  | State
Guy Avenue | Palmerston North | Palmerston North City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-12-01 | 2024-07-02 | 2024-07-02 | 2025-03-27 | House | 1 |  |  |  | 1 |  |  |  | State
Margaret Street | Invercargill | Invercargill City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-11-01 | 2023-11-22 | 2024-02-05 | 2024-10-08 | House | 2 |  |  |  | 2 |  |  |  | State
South Road | Dunedin | Dunedin City | Contracted/Construction | Construction | Acquired new | Yes | Yes | 2023-06-15 | 2023-09-15 | 2024-02-09 | 2024-11-13 | Terrace | 4 |  |  | 2 | 2 |  |  |  | State
Beauchamp & Reverie | Massey | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2022-06-20 | 2023-09-15 |  | 2026-11-12 | House | 11 |  |  |  | 8 | 3 |  |  | State
Beauchamp & Reverie | Massey | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2022-06-20 | 2023-09-15 |  | 2026-11-12 | Walk-up | 54 |  | 6 | 48 |  |  |  |  | State
Surrey Crescent | Grey Lynn | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-05-10 |  |  | 2026-04-29 | Apartment | 36 |  |  | 32 | 4 |  |  |  | State
Evans Bay Parade | Wellington | Wellington City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2022-05-09 |  |  | 2027-06-21 | Apartment | 76 |  | 36 | 40 |  |  |  |  | State
Evans Bay Parade | Wellington | Wellington City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2022-05-09 |  |  | 2027-06-21 | Duplex | 4 |  |  |  |  | 4 |  |  | State
Crete Street & Salonika Street | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-02-15 |  |  | 2025-09-30 | House | 6 |  |  | 2 | 3 | 1 |  |  | State
Aotaki Street | Otaki | Kapiti Coast District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-05 |  |  | 2026-06-30 | Duplex | 6 |  | 6 | [5 empty] | State
Stirling Crescent | Dunedin | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-01-29 | 2024-04-02 |  | 2025-09-30 | House | 3 |  | 3 | [5 empty] | State
Atawhai Drive | Nelson | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-04-28 | House | 18 |  | 3 | 12 |  | 3 |  |  | State
Crewe Cres & Bolton Place | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-02-01 |  |  | 2026-03-31 | House | 8 |  |  |  | 2 | 4 | 2 |  | State
Crewe Cres & Bolton Place | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-02-01 |  |  | 2026-03-31 | Walk-up | 31 |  |  | 31 |  |  |  |  | State
Endeavour Avenue | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-08-11 |  |  | 2027-01-29 | Duplex | 16 |  |  |  | 16 |  |  |  | State
Endeavour Avenue | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-08-11 |  |  | 2027-01-29 | Duplex | 16 |  |  |  | 16 |  |  |  | State
Endeavour Avenue | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-08-11 |  |  | 2027-01-29 | House | 3 |  |  |  |  | 2 | 1 |  | State
Endeavour Avenue | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-08-11 |  |  | 2027-01-29 | House | 6 |  |  |  |  | 5 | 1 |  | State
Endeavour Avenue | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-08-11 |  |  | 2027-01-29 | Walk-up | 19 |  |  | 19 |  |  |  |  | State
Collins Road | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-12-21 |  |  | 2026-05-15 | Duplex | 8 |  |  | 2 |  | 6 |  |  | State
Collins Road | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-12-21 |  |  | 2026-05-15 | House | 3 |  | 3 | [5 empty] | State
Collins Road | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-12-21 |  |  | 2026-05-15 | Terrace | 30 |  |  | 30 |  |  |  |  | State
Collins Road | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-12-21 |  |  | 2026-05-15 | Walk-up | 6 |  | 4 | 2 |  |  |  |  | State
Brentwood Ave & Croydon Ave & Botanical Road | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-13 | Duplex | 2 | [5 empty] | 2 |  | State
Brentwood Ave & Croydon Ave & Botanical Road | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-13 | House | 3 |  |  |  |  | 1 | 2 |  | State
Brentwood Ave & Croydon Ave & Botanical Road | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-13 | Terrace | 6 |  |  | 6 |  |  |  |  | State
Brentwood Ave & Croydon Ave & Botanical Road | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-13 | Walk-up | 24 |  | 6 | 18 |  |  |  |  | State
High Street | Motueka | Tasman District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 7 |  | 3 | 4 |  |  |  |  | State
Brandon Road | Glen Eden | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2020-09-30 | 2023-05-02 |  | 2025-08-12 | Walk-up | 35 |  | 11 | 18 | 6 |  |  |  | State
Rockfield Rd & Edmonton Ave | Oranga | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-03-22 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Rockfield Rd & Edmonton Ave | Oranga | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-03-22 | House | 4 |  |  |  |  | 4 |  |  | State
Rockfield Rd & Edmonton Ave | Oranga | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-03-22 | Terrace | 30 |  |  | 24 | 6 |  |  |  | State
Rockfield Rd & Edmonton Ave | Oranga | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-03-22 | Walk-up | 6 |  | 6 | [5 empty] | State
Greers Road & Truman Road | Bryndwr | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-10-02 | 2024-06-04 |  | 2025-07-21 | Duplex | 4 |  |  |  |  | 4 |  |  | State
Greers Road & Truman Road | Bryndwr | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-10-02 | 2024-06-04 |  | 2025-07-21 | Walk-up | 12 |  | 2 | 10 |  |  |  |  | State
Kowhai Street & Harris Street | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-04-03 | 2024-04-09 |  | 2025-12-05 | Duplex | 12 |  |  | 8 | 2 | 2 |  |  | State
Kowhai Street & Harris Street | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-04-03 | 2024-04-09 |  | 2025-12-05 | House | 13 |  |  | 2 | 6 | 3 | 2 |  | State
Greers Road & Truman Road | Bishopdale | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-06-11 |  |  | 2025-09-30 | House | 3 |  | 3 | [5 empty] | State
Calliope Cres, Castor Cres & Hazard Gr | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-09-21 | 2024-02-15 |  | 2025-10-01 | Duplex | 4 |  |  | 2 | 1 | 1 |  |  | State
Calliope Cres, Castor Cres & Hazard Gr | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-09-21 | 2024-02-15 |  | 2025-10-01 | House | 5 |  |  |  |  | 3 |  | 2 | State
Young Gr & George St | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-10-27 | 2024-01-31 |  | 2026-06-30 | Mixed | 6 |  | 5 | 1 |  |  |  |  | State
Poole Street | Lower Hutt | Lower Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 4 |  | 4 | [5 empty] | State
Riccarton Road | Riccarton | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-07-09 | Duplex | 14 |  |  | 4 | 8 | 2 |  |  | State
Riccarton Road | Riccarton | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-07-09 | House | 2 |  |  |  |  | 2 |  |  | State
Riccarton Road | Riccarton | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-07-09 | Walk-up | 20 |  |  | 20 |  |  |  |  | State
Oxford Terrace | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-09-28 | 2024-04-12 |  | 2025-10-21 | Walk-up | 15 |  | 12 | 3 |  |  |  |  | State
Oxford Terrace & Lincoln Avenue | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-04-14 | 2024-03-18 |  | 2025-11-24 | Walk-up | 15 |  |  | 15 |  |  |  |  | State
Athlone Cres & Stellin Street | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-07-07 | 2024-03-22 |  | 2025-11-14 | Apartment | 16 |  |  | 16 |  |  |  |  | State
Hendon Avenue | Mount Albert | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2020-11-12 |  |  | 2027-03-31 | Apartment | 50 |  |  | 30 | 20 |  |  |  | State
Osterley Way | Manukau | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2022-08-09 |  |  | 2027-05-06 | Apartment | 123 |  |  | 123 |  |  |  |  | State
Bisset Road | Kaikohe | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-03-25 | House | 1 |  | 1 | [5 empty] | State
Purdy Street | Kaikohe | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-16 | House | 2 |  |  | 2 |  |  |  |  | State
Guerin Street | Kaikohe | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-18 | House | 1 |  |  |  | 1 |  |  |  | State
Guerin Street | Kaikohe | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-26 | House | 1 |  |  |  | 1 |  |  |  | State
Pukepoto Rd & Tangonge Cres | Katikati | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 10 |  | 10 | [5 empty] | State
Kowhai Avenue | Kaikohe | Far North District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2022-10-11 | 2023-04-17 |  | 2025-07-17 | Duplex | 2 |  |  | 2 |  |  |  |  | State
Kowhai Avenue | Kaikohe | Far North District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2022-10-11 | 2023-04-17 |  | 2025-07-17 | Duplex | 2 |  |  | 2 |  |  |  |  | State
Kowhai Avenue | Kaikohe | Far North District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2022-10-11 | 2023-04-17 |  | 2025-07-17 | House | 3 |  |  |  | 1 | 2 |  |  | State
Ngatiapa St & Tukanae St | Strathmore Park | Wellington City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-11-12 | Duplex | 8 |  |  | 4 |  | 4 |  |  | State
Ngatiapa St & Tukanae St | Strathmore Park | Wellington City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-11-12 | House | 6 |  |  |  |  | 1 | 5 |  | State
Ngatiapa St & Tukanae St | Strathmore Park | Wellington City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-11-12 | Walk-up | 36 |  |  | 18 | 18 |  |  |  | State
Wood Street | Lower Hutt | Lower Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-19 | House | 35 |  |  | 7 | 20 | 8 |  |  | State
Nuku Street | Wellington | Wellington City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-23 |  |  | 2026-11-12 | House | 4 |  |  |  | 4 |  |  |  | State
Nuku Street | Wellington | Wellington City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-23 |  |  | 2026-11-12 | Terrace | 10 |  |  |  | 5 | 5 |  |  | State
Nuku Street | Wellington | Wellington City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-23 |  |  | 2026-11-12 | Walk-up | 26 |  | 8 | 18 |  |  |  |  | State
Vallance Place | Massey | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 13 |  | 6 |  | 6 | 1 |  |  | State
Aspen Street & Victor Street | Avondale | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2022-08-17 |  |  | 2027-03-03 | Apartment | 16 |  |  | 6 | 10 |  |  |  | State
Aspen Street & Victor Street | Avondale | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2022-08-17 |  |  | 2027-03-03 | Walk-up | 5 |  |  | 5 |  |  |  |  | State
Church Street | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-11-17 |  |  | 2026-08-28 | Duplex | 24 |  | 4 | 20 |  |  |  |  | State
Church Street | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-11-17 |  |  | 2026-08-28 | Walk-up | 39 |  | 10 | 29 |  |  |  |  | State
Weymouth Road | Weymouth | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2022-09-28 |  |  | 2026-05-26 | Apartment | 48 |  | 12 | 36 |  |  |  |  | State
Graham Street | Blenheim | Marlborough District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-06-06 |  |  | 2026-02-20 | House | 3 |  |  | 1 |  |  | 2 |  | State
Kendal Avenue | Burnside | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-06-07 | 2023-10-27 |  | 2025-12-12 | Duplex | 10 |  |  | 10 |  |  |  |  | State
Lynton Road | Mt Wellington | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-09-22 |  |  | 2025-11-20 | Apartment | 50 |  | 38 | 12 |  |  |  |  | State
Meola Road | Westmere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-12 |  |  | 2026-06-30 | Terrace | 7 |  | 7 | [5 empty] | State
Newcastle Terrace | Mount Albert | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-21 |  |  | 2026-06-30 | Terrace | 6 |  | 2 | 4 |  |  |  |  | State
Hendon Avenue | Mount Albert | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-06-24 |  |  | 2026-03-25 | Apartment | 10 |  |  | 5 | 5 |  |  |  | State
Richardson Road | Owairaka | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-06-14 |  |  | 2026-06-30 | Terrace | 1 | [5 empty] | 1 |  | State
Owairaka Avenue | Owairaka | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2021-06-24 |  |  | 2026-04-23 | Apartment | 10 |  |  | 10 |  |  |  |  | State
Alfred St & Church St | Onehunga | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-03-24 |  |  | 2026-11-23 | Apartment | 29 |  | 29 | [5 empty] | State
Amy Street | Ellerslie | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-24 |  |  | 2026-06-30 | Duplex | 8 |  | 2 |  | 6 |  |  |  | State
Albrecht Ave & Quona Ave | Waikowhai | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-10-09 | Duplex | 16 |  |  | 8 | 6 | 2 |  |  | State
Albrecht Ave & Quona Ave | Waikowhai | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-10-09 | House | 5 |  |  | 1 | 2 | 2 |  |  | State
Bader Dr | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2021-06-29 | 2023-04-26 |  | 2026-03-18 | Terrace | 3 |  |  |  |  | 3 |  |  | State
Bader Dr | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2021-06-29 | 2023-04-26 |  | 2026-03-18 | Walk-up | 15 |  |  | 9 | 6 |  |  |  | State
Tiki Place & Peter Snell Rd | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 18 |  | 7 | 11 |  |  |  |  | State
Arron Street | Ellerslie | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  |  | 1 | 2 |  |  |  | State
Hargest Tce & Alamein Tce | Owairaka | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-11-07 |  |  | 2025-11-12 | Walk-up | 42 |  |  | 30 | 12 |  |  |  | State
Winthrop Way & Mayflower Cres | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2022-11-18 |  |  | 2026-09-04 | Walk-up | 23 |  |  | 17 | 6 |  |  |  | State
Walmer Road | Pt Chevalier | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-11 |  |  | 2026-06-30 | Duplex | 4 |  |  | 1 | 3 |  |  |  | State
Roscommon Road | Clendon Park | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2022-08-08 | 2024-02-19 |  | 2025-12-04 | Apartment | 29 |  | 13 | 16 |  |  |  |  | State
Allen Bell Dr | Kaitaia | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-10-20 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Allen Bell Dr | Kaitaia | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-10-20 | House | 2 |  |  |  | 1 | 1 |  |  | State
Rugby St & Raleigh St | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-07 | 2024-05-06 |  | 2026-03-31 | Duplex | 14 |  |  | 10 | 4 |  |  |  | State
Rugby St & Raleigh St | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-07 | 2024-05-06 |  | 2026-03-31 | House | 14 |  |  |  | 1 | 9 | 4 |  | State
Rugby St & Raleigh St | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-07 | 2024-05-06 |  | 2026-03-31 | Terrace | 22 |  | 14 | 8 |  |  |  |  | State
Rugby St & Raleigh St | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-07 | 2024-05-06 |  | 2026-03-31 | Walk-up | 8 |  | 8 | [5 empty] | State
Bremner Avenue | Mt Roskill | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-09 |  |  | 2026-06-30 | House | 2 |  |  |  | 2 |  |  |  | State
Hollyford Ave & Earnslaw Cres | Bryndwr | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-08-16 |  |  | 2026-05-25 | Duplex | 2 |  |  | 2 |  |  |  |  | State
Hollyford Ave & Earnslaw Cres | Bryndwr | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-08-16 |  |  | 2026-05-25 | House | 6 |  |  |  | 3 | 3 |  |  | State
Hollyford Ave & Earnslaw Cres | Bryndwr | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-08-16 |  |  | 2026-05-25 | Terrace | 6 |  |  | 6 |  |  |  |  | State
Hollyford Ave & Earnslaw Cres | Bryndwr | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-08-16 |  |  | 2026-05-25 | Walk-up | 12 |  |  | 12 |  |  |  |  | State
Sandringham Rd & Harwood St | Sandringham | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-03-31 |  |  | 2026-03-27 | Apartment | 24 |  | 19 | 5 |  |  |  |  | State
Kupe St & Hawaiki St | Orakei | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-06-29 | Walk-up | 14 |  | 1 | 9 | 4 |  |  |  | State
South Street | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-20 |  |  | 2026-06-30 | House | 9 |  | 5 | 2 | 2 |  |  |  | State
Coventry St & Farnham Ave & Croydon Ave | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-13 | Duplex | 4 |  |  |  |  | 4 |  |  | State
Coventry St & Farnham Ave & Croydon Ave | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-13 | House | 2 | [5 empty] | 2 |  | State
Coventry St & Farnham Ave & Croydon Ave | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-13 | Terrace | 10 |  |  | 10 |  |  |  |  | State
Coventry St & Farnham Ave & Croydon Ave | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-13 | Walk-up | 18 |  | 1 | 17 |  |  |  |  | State
Bledisloe Road | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-02-12 |  |  | 2025-11-21 | Duplex | 10 |  |  | 8 | 2 |  |  |  | State
Bledisloe Road | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-02-12 |  |  | 2025-11-21 | House | 1 |  |  |  |  | 1 |  |  | State
Bledisloe Road | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-02-12 |  |  | 2025-11-21 | Walk-up | 8 |  |  | 8 |  |  |  |  | State
School Road | Morningside | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-11 | Apartment | 41 |  | 30 | 11 |  |  |  |  | State
Rolleston Street | Thames | Thames-Coromandel District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-06 |  |  | 2026-06-30 | House | 2 |  |  | 2 |  |  |  |  | State
Paramount Parade | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-19 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Paramount Parade | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-19 | House | 3 |  |  |  |  | 2 | 1 |  | State
Paramount Parade | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-19 | Walk-up | 12 |  |  | 12 |  |  |  |  | State
Paramount Parade & Hawea Pl | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-11-13 | Duplex | 2 |  |  |  |  | 2 |  |  | State
Paramount Parade & Hawea Pl | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-11-13 | House | 11 |  |  |  |  | 7 | 4 |  | State
Paramount Parade & Hawea Pl | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-11-13 | Walk-up | 8 |  | 1 | 7 |  |  |  |  | State
Rutherford Rd | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-22 |  |  | 2026-06-30 | House | 1 |  |  |  | 1 |  |  |  | State
Colston Street | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-22 |  |  | 2026-06-30 | Duplex | 3 |  | 2 | 1 |  |  |  |  | State
Whites Line East | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-06-22 | 2024-04-03 |  | 2025-11-11 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Hamua Grv | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-04-03 | 2023-11-09 |  | 2025-09-30 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Hamua Grv | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-04-03 | 2023-11-09 |  | 2025-09-30 | House | 2 |  |  | 1 |  | 1 |  |  | State
Castor Cres & Miranda St | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-04-17 |  |  | 2025-07-18 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Castor Cres & Miranda St | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-04-17 |  |  | 2025-07-18 | Terrace | 5 |  |  |  | 5 |  |  |  | State
Castor Cres | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-06-27 |  |  | 2025-07-18 | Duplex | 6 |  |  | 4 | 2 |  |  |  | State
Cornwall Cres | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-04-06 | 2023-06-27 |  | 2025-07-18 | House | 2 |  |  | 2 |  |  |  |  | State
Westmeath St & Warspite Ave | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-04-14 |  |  | 2025-07-18 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Corinna Street | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-07-17 |  |  | 2025-07-18 | Duplex | 2 |  | 1 | 1 |  |  |  |  | State
Corinna Street | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-07-17 |  |  | 2025-07-18 | Terrace | 5 |  |  | 5 |  |  |  |  | State
Cheshire Street | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-06-19 |  |  | 2025-07-18 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Cheshire Street | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-06-19 |  |  | 2025-07-18 | House | 2 |  |  |  | 2 |  |  |  | State
Westmeath Street | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-04-17 | 2023-06-27 |  | 2025-07-18 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Warspite Avenue | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-08-14 |  |  | 2025-07-18 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Warspite Avenue | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-08-14 |  |  | 2025-07-18 | Terrace | 7 |  |  | 7 |  |  |  |  | State
Ford Street | Opotiki | Opotiki District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-09-19 |  |  | 2025-09-30 | House | 11 |  |  | 3 | 6 | 2 |  |  | State
Upham Terrace | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-23 |  |  | 2026-06-30 | Mixed | 3 |  | 1 | 2 |  |  |  |  | State
King Street | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-07-10 | 2024-03-22 |  | 2025-07-23 | Duplex | 4 |  |  | 4 |  |  |  |  | State
King Street | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-07-10 | 2024-03-22 |  | 2025-07-23 | House | 1 | [5 empty] | 1 |  | State
Alverstoke Rd | Tauranga | Tauranga City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 2 | 1 |  |  |  |  | State
Te Whiti Grove | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-04-08 | 2024-05-01 |  | 2026-06-30 | Mixed | 3 |  |  | 2 | 1 |  |  |  | State
Domain Road | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-07-10 | 2024-02-09 |  | 2025-12-17 | Duplex | 2 |  |  | 2 |  |  |  |  | State
Domain Road | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-07-10 | 2024-02-09 |  | 2025-12-17 | House | 2 | [5 empty] | 2 |  | State
Albertson Avenue | Dunedin | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-05-17 |  |  | 2025-09-30 | Duplex | 6 |  |  | 6 |  |  |  |  | State
Albertson Avenue | Dunedin | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-05-17 |  |  | 2025-09-30 | House | 5 |  | 1 | 2 | 2 |  |  |  | State
Doon Street | Mosgiel | Dunedin City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 3 | 2 | 1 | [5 empty] | State
Gretna Place & Doon Street | Mosgiel | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-03-04 | 2024-08-01 |  | 2026-06-30 | Mixed | 11 |  | 7 | 2 | 2 |  |  |  | State
Spey St & Doon St | Mosgiel | Dunedin City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 4 |  | 2 | 1 | 1 |  |  |  | State
Colson Street | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-07-03 | 2024-06-06 |  | 2026-06-30 | House | 3 |  | 2 |  | 1 |  |  |  | State
Feist St & Seddon St & Newcombe St | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-12-12 | 2024-06-24 |  | 2026-06-30 | Mixed | 11 |  | 8 | 2 | 1 |  |  |  | State
Valonia Street | New Windsor | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2022-02-16 | 2022-04-26 |  | 2026-06-30 | Mixed | 3 |  |  | 1 | 2 |  |  |  | State
Terence Street | Taupo | Taupo District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 2 |  | 1 | 1 |  |  | State
Carroll Street | Dunedin | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-12-12 |  |  | 2026-12-10 | Apartment | 41 |  | 19 | 22 |  |  |  |  | State
Dominion Road | Mount Roskill | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2022-05-20 |  |  | 2025-09-30 | Walk-up | 12 |  | 6 | 6 |  |  |  |  | State
Hei Hei Road | Hei Hei | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-09-30 | House | 3 |  |  | 3 |  |  |  |  | State
Redmond Street | Tauranga | Tauranga City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-12-19 | 2024-05-05 |  | 2026-03-11 | Duplex | 10 |  |  | 6 | 4 |  |  |  | State
Redmond Street | Tauranga | Tauranga City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-12-19 | 2024-05-05 |  | 2026-03-11 | House | 1 |  |  |  | 1 |  |  |  | State
Redmond Street | Tauranga | Tauranga City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-12-19 | 2024-05-05 |  | 2026-03-11 | House | 5 |  |  | 1 | 2 | 2 |  |  | State
Wynyard Cres | Napier | Napier City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 1 |  |  |  |  | 1 |  |  | State
Lipscombe Cres | Havelock North | Hastings District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 1 | [7 empty] | State
Crosher Place | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-11-21 |  |  | 2025-09-30 | Terrace | 5 |  |  |  | 5 |  |  |  | State
Examiner Street | Nelson | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-05-25 | Apartment | 29 |  | 17 | 12 |  |  |  |  | State
Rimutaka Street | Upper Hutt | Upper Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-08-30 | 2024-07-19 |  | 2026-06-30 | Mixed | 20 |  | 12 | 6 | 2 |  |  |  | State
Gardiner Street | Blenheim | Marlborough District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-08-07 | 2024-04-05 |  | 2026-02-20 | Duplex | 2 |  |  | 2 |  |  |  |  | State
Gardiner Street | Blenheim | Marlborough District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-08-07 | 2024-04-05 |  | 2026-02-20 | House | 4 |  |  | 4 |  |  |  |  | State
Hutcheson Street | Blenheim | Marlborough District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-09-25 |  |  | 2025-12-18 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Hutcheson Street | Blenheim | Marlborough District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-09-25 |  |  | 2025-12-18 | House | 6 |  |  |  | 3 | 3 |  |  | State
Muller Rd & Weld St | Blenheim | Marlborough District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-02-28 |  |  | 2026-02-20 | Duplex | 4 |  |  | 4 |  |  |  |  | State
Muller Rd & Weld St | Blenheim | Marlborough District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-02-28 |  |  | 2026-02-20 | House | 1 |  |  |  |  | 1 |  |  | State
Meachen Cres | Blenheim | Marlborough District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 3 | [5 empty] | State
Coxhead Road & Thompson Terrace | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-02-28 |  |  | 2025-10-13 | Duplex | 2 | [5 empty] | 2 |  | State
Coxhead Road & Thompson Terrace | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-02-28 |  |  | 2025-10-13 | House | 6 |  |  |  | 2 | 1 | 3 |  | State
Coxhead Road & Thompson Terrace | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-02-28 |  |  | 2025-10-13 | Terrace | 14 |  |  | 8 | 6 |  |  |  | State
Clutha Cres & Awatere St | Clover Park | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-06-07 |  |  | 2025-09-30 | Duplex | 2 | [5 empty] | 2 |  | State
Clutha Cres & Awatere St | Clover Park | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-06-07 |  |  | 2025-09-30 | House | 2 |  |  |  | 1 |  | 1 |  | State
Clutha Cres & Awatere St | Clover Park | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-06-07 |  |  | 2025-09-30 | Terrace | 5 |  |  | 5 |  |  |  |  | State
Lowe Avenue | Thames | Thames-Coromandel District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Duplex | 6 |  | 2 | 2 | 2 |  |  |  | State
Lister Cres & Geddis Ave | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-10-31 |  |  | 2026-04-24 | Duplex | 24 |  |  | 10 | 8 | 6 |  |  | State
Lister Cres & Geddis Ave | Napier | Napier City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-10-31 |  |  | 2026-04-24 | House | 6 |  |  |  | 1 | 4 | 1 |  | State
Lyall Place | Bryndwr | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-12-14 | 2024-05-02 |  | 2025-08-06 | House | 3 |  |  | 2 | 1 |  |  |  | State
Collingwood St | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-01-31 | 2024-04-26 |  | 2026-06-30 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State
Coventry Street & Hull Place | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-20 |  |  | 2025-07-09 | Duplex | 6 |  |  | 4 | 2 |  |  |  | State
Coventry Street & Hull Place | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-20 |  |  | 2025-07-09 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Coventry Street & Hull Place | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-20 |  |  | 2025-07-09 | House | 1 |  |  |  |  | 1 |  |  | State
Ranolf Street & Malfroy Street | Rotorua | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-04-28 | Walk-up | 24 |  | 5 | 19 |  |  |  |  | State
Raurenga Avenue | Royal Oak | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-07-12 | 2024-05-14 |  | 2025-10-20 | Walk-up | 24 |  | 24 | [5 empty] | State
Thomas Street | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 8 |  | 4 | 2 | 2 |  |  |  | State
Strange Street | Waitara | New Plymouth District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-07-19 | 2024-07-19 |  | 2026-06-30 | Mixed | 4 |  | 3 |  | 1 |  |  |  | State
Reid Road | New Lynn | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-25 | Apartment | 47 |  | 10 | 32 | 5 |  |  |  | State
Wrantage Street | New Plymouth | New Plymouth District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 6 |  | 4 | 2 |  |  |  |  | State
Budleigh St | New Plymouth | New Plymouth District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-06-07 | 2024-07-01 |  | 2026-06-30 | Mixed | 9 |  | 6 | 2 | 1 |  |  |  | State
Grandview Rd | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-06-27 |  |  | 2026-06-30 | Mixed | 6 |  | 6 | [5 empty] | State
Yvonne Street | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-06-29 | 2023-12-20 |  | 2025-09-30 | Duplex | 4 |  |  | 2 | 2 |  |  |  | State
Cascades Rd | Pakuranga | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-24 |  |  | 2026-06-30 | Mixed | 9 |  | 6 |  | 3 |  |  |  | State
Bisset Road | Kaikohe | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-03-04 | House | 41 |  |  |  | 22 | 8 | 11 |  | State
King St & Stewart St & Washer Ave | Whakatane | Whakatane District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-01-14 | Duplex | 2 |  |  |  | 2 |  |  |  | State
King St & Stewart St & Washer Ave | Whakatane | Whakatane District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-01-14 | Terrace | 15 |  |  | 13 | 2 |  |  |  | State
King St & Stewart St & Washer Ave | Whakatane | Whakatane District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-01-14 | Walk-up | 36 |  | 12 | 24 |  |  |  |  | State
Bremner Avenue | Mt Roskill | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-09 |  |  | 2026-06-30 | House | 2 |  |  |  | 2 |  |  |  | State
Marriotts Road & Rookwood Ave | New Brighton | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-06-09 | 2024-01-31 |  | 2025-09-02 | Duplex | 10 |  |  |  | 10 |  |  |  | State
Marriotts Road & Rookwood Ave | New Brighton | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-06-09 | 2024-01-31 |  | 2025-09-02 | House | 2 |  |  |  |  | 2 |  |  | State
King Street | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 9 |  | 2 | 4 | 2 |  |  |  | State
Rongomai Road | Otara | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-08-21 | 2024-09-17 |  | 2026-06-30 | Mixed | 18 |  | 6 | 6 | 2 | 4 |  |  | State
Childers Rd & Totara St | Gisborne | Gisborne District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 12 |  | 7 | 5 |  |  |  |  | State
Lovelock Street | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-02 | 2024-02-23 |  | 2025-10-17 | Duplex | 7 |  |  |  | 3 | 4 |  |  | State
Donald Road | Kaitaia | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-08-26 | House | 15 |  |  |  | 12 | 3 |  |  | State
Weymouth Rd | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-01-25 |  |  | 2026-03-02 | Walk-up | 24 |  |  | 12 | 12 |  |  |  | State
Bishops Lane | Nelson | Hamilton City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 5 |  | 4 |  | 1 |  |  |  | State
Heath Street | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-06-23 |  |  | 2025-09-30 | Duplex | 4 |  |  |  | 4 |  |  |  | State
Farmer Cres | Lower Hutt | Lower Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 15 |  |  | 15 |  |  |  |  | State
Fairmont Street | Ngaruawahia | Waikato District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 4 |  |  |  | 4 |  |  |  | State
Price Terrace | Matamata | Matamata-Piako District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 8 |  |  | 8 |  |  |  |  | State
Apanui Avenue & Pounama Place | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-12-06 |  |  | 2025-07-01 | Duplex | 6 |  |  | 4 | 2 |  |  |  | State
Apanui Avenue & Pounama Place | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-12-06 |  |  | 2025-07-01 | House | 8 |  |  | 6 |  | 1 | 1 |  | State
Taingi St & Tiki Pl | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 32 |  | 15 | 8 | 9 | 9 |  |  | State
Weaver Street | Whangarei | Whangarei District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-25 |  |  | 2026-12-01 | Terrace | 18 |  |  | 18 |  |  |  |  | State
Grey Road | Timaru | Timaru District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Duplex | 4 |  | 4 | [5 empty] | State
Grey Road | Timaru | Timaru District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 18 |  |  | 7 | 5 | 4 | 2 |  | State
Grey Road | Timaru | Timaru District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Terrace | 16 |  |  | 16 |  |  |  |  | State
Ferry Road & Ollivier Rd | Christchurch | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-06-17 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Ferry Road & Ollivier Rd | Christchurch | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-06-17 | House | 4 |  |  |  | 1 | 1 | 1 | 1 | State
Ferry Road & Ollivier Rd | Christchurch | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-06-17 | Terrace | 9 |  |  | 9 |  |  |  |  | State
Ferry Road & Ollivier Rd | Christchurch | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-06-17 | Walk-up | 24 |  | 15 | 9 |  |  |  |  | State
Saxby Grv & Judd Cres | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-04 |  |  | 2026-06-30 | House | 3 |  | 2 |  |  |  | 1 |  | State
Church Street | Ashburton | Ashburton District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-06-24 | 2024-07-16 |  | 2026-06-30 | Mixed | 13 |  | 8 | 2 | 3 |  |  |  | State
Orr Street | Ashburton | Ashburton District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-04 |  |  | 2026-06-30 | Mixed | 9 |  | 7 | 2 |  |  |  |  | State
Arthur Street | Blenheim | Marlborough District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes |  | 2024-07-15 |  | 2026-06-30 | Mixed | 10 |  | 6 | 3 | 1 |  |  |  | State
Wihongi St | Kaikohe | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 1 | [5 empty] | 1 |  | State
Middlebrook Drive | Katikati | Western Bay of Plenty District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-26 |  |  | 2025-07-01 | House | 18 |  | 6 | 8 | 4 |  |  |  | State
Pakuranga Rd | Pakuranga | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Walk-up | 6 | 6 | [6 empty] | State
Fantame St North | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-05-30 |  |  | 2027-06-23 | House | 2 |  |  |  |  | 1 | 1 |  | State
Fantame St North | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-05-30 |  |  | 2027-06-23 | Terrace | 11 |  |  |  | 11 |  |  |  | State
Fantame St North | Porirua | Porirua City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-05-30 |  |  | 2027-06-23 | Walk-up | 21 |  | 1 | 20 |  |  |  |  | State
Garaway Street | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-09-12 | 2024-02-09 |  | 2025-10-16 | Duplex | 6 |  |  | 2 | 4 |  |  |  | State
Garaway Street | Whakatane | Whakatane District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-09-12 | 2024-02-09 |  | 2025-10-16 | House | 2 |  |  |  |  | 2 |  |  | State
Morrison Avenue | Northcote | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-08 | 2024-04-26 |  | 2026-06-30 | House | 6 |  | 4 |  | 2 |  |  |  | State
Hoffman Street | Hokitika | Westland District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-08-30 | 2023-09-11 |  | 2025-12-11 | House | 6 |  | 4 | 2 |  |  |  |  | State
Jollie Street | Hokitika | Westland District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-07-19 | 2023-09-27 |  | 2026-02-20 | Duplex | 2 |  |  | 2 |  |  |  |  | State
Jollie Street | Hokitika | Westland District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-07-19 | 2023-09-27 |  | 2026-02-20 | House | 2 |  |  | 2 |  |  |  |  | State
Palmerston Street | Westport | Buller District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-07-01 | House | 8 |  | 8 | [5 empty] | State
Thomas Street | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Terrace | 5 |  | 3 | 1 | 1 |  |  |  | State
Thomas Street | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 10 |  | 6 | 2 |  | 2 |  |  | State
Steere Place | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 6 |  | 4 | 2 |  |  |  |  | State
Friedlanders Road | Manurewa | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 5 |  |  |  | 3 | 2 |  |  | State
Selago Place | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-01 |  |  | 2026-06-30 | Mixed | 3 |  |  | 2 |  |  | 1 |  | State
Addington Ave & Harrow Place | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-08 |  |  | 2026-06-30 | Mixed | 7 |  |  | 1 | 5 | 1 |  |  | State
Waimea Road | Nelson | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-12-12 | Duplex | 8 |  | 8 | [5 empty] | State
Kawai Street | Nelson | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-10-16 | Duplex | 2 |  |  | 2 |  |  |  |  | State
Kawai Street | Nelson | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-10-16 | House | 2 |  |  | 1 | 1 |  |  |  | State
Campbell Street | Nelson | Nelson City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-03-26 |  |  | 2025-10-23 | House | 3 |  |  |  | 2 |  | 1 |  | State
Tipahi Street | Nelson | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 10 |  | 6 | 3 | 1 |  |  |  | State
Stonex Road | Papatoetoe | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 2 |  |  |  | 1 | 1 |  |  | State
Haughey Avenue | Three Kings | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-03-23 | 2024-05-10 |  | 2026-06-30 | House | 2 | [5 empty] | 2 |  | State
Seabrook Avenue | New Lynn | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 3 |  |  | 2 | 1 |  |  |  | State
Wellington Street | Pukekohe | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 12 |  | 2 | 3 | 5 | 2 |  |  | State
Albertson Street | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-15 |  |  | 2026-06-30 | House | 2 |  | 1 |  |  |  | 1 |  | State
Churchill Avenue | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-01-25 | 2024-01-23 |  | 2026-06-30 | House | 2 |  |  |  |  | 2 |  |  | State
Roscommon Road | Clendon Park | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-30 |  |  | 2026-06-30 | Mixed | 5 |  |  | 2 | 2 |  | 1 |  | State
Surrey Street | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-07-03 | 2024-07-31 |  | 2026-06-30 | House | 2 |  |  |  |  | 2 |  |  | State
East Street | Greytown | South Wairarapa District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-10-16 | 2024-04-05 |  | 2025-07-07 | House | 4 |  |  |  | 3 |  | 1 |  | State
Friedlanders Road | Manurewa | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 7 |  |  |  | 5 | 2 |  |  | State
Friedlanders Road | Manurewa | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 5 |  |  | 3 | 2 |  |  |  | State
Morris Street | Dunedin | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-10-12 | 2024-04-17 |  | 2026-06-30 | Mixed | 5 |  | 3 | 2 |  |  |  |  | State
Thames Street | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State
Girling Avenue | Blenheim | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 1 | 2 |  |  |  |  | State
Charles Street | Feilding | Manawatu District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-05-14 | 2024-05-13 |  | 2026-06-30 | House | 2 |  | 1 |  | 1 |  |  |  | State
Taumahi Street | Whanganui | Rangitikei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 1 | 2 |  |  |  |  | State
Morris Street | Marton | Rangitikei District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-10 |  |  | 2026-06-30 | Mixed | 3 |  | 2 | 1 |  |  |  |  | State
Tweed Street | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-09-06 | 2024-02-16 |  | 2026-06-30 | Duplex | 4 |  | 4 | [5 empty] | State
Galway Avenue | Palmerston North | Palmerston North City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-06-17 | 2024-02-19 |  | 2026-06-30 | Mixed | 3 |  | 1 |  | 2 |  |  |  | State
Hamilton Street | Gore | Gore District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-01-14 | Duplex | 14 |  | 6 | 8 |  |  |  |  | State
Hamilton Street | Gore | Gore District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-01-14 | House | 10 |  | 1 | 2 | 4 | 2 | 1 |  | State
Jersey Avenue | Mount Albert | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-07-26 | 2024-08-07 |  | 2026-06-30 | House | 3 |  |  |  | 2 |  | 1 |  | State
Tasman Avenue | Mount Albert | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-05-31 | 2023-07-29 |  | 2026-06-30 | Mixed | 5 |  |  | 2 | 3 |  |  |  | State
Ferguson Street | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-15 |  |  | 2026-06-30 | House | 2 |  |  |  | 2 |  |  |  | State
Solo Place & Astor Place | Manurewa | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-02-28 | 2024-06-18 |  | 2026-06-30 | Mixed | 6 |  |  |  | 4 |  | 2 |  | State
Baker Street & Leather Street | Huntly | Waikato District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-05-27 |  |  | 2026-06-30 | House | 6 |  | 2 | 2 | 2 |  |  |  | State
Russell Street | Westport | Buller District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-07-01 | House | 2 |  |  | 2 |  |  |  |  | State
Clements Street | Otahuhu | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-21 |  |  | 2026-06-30 | Mixed | 5 |  |  |  | 3 | 2 |  |  | State
Doralto Road | New Plymouth | New Plymouth District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-05-22 | 2024-05-16 |  | 2026-06-30 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State
Fairfiled Road | Hawera | South Taranaki District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 | 2 | 1 | [5 empty] | State
Reid Avenue | Hawera | South Taranaki District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 2 |  | 1 |  |  |  | State
Barton Grove | Naenae | Lower Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  |  | 2 | 1 |  |  |  | State
Compton Cres & Pike Street | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-11 |  |  | 2026-06-30 | House | 7 | 1 | 1 | 5 |  |  |  |  | State
Avenue Road | Otahuhu | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-04-26 |  |  | 2026-06-30 | House | 2 |  |  | 1 | 1 |  |  |  | State
Esk Place Block | Porirua | Porirua City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-02-17 | Duplex | 26 |  |  | 16 | 10 |  |  |  | State
Esk Place Block | Porirua | Porirua City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-02-17 | House | 6 |  |  | 1 | 1 |  | 4 |  | State
Esk Place Block | Porirua | Porirua City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2027-02-17 | Walk-up | 22 |  | 22 | [5 empty] | State
District Road | Dunedin | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-26 |  |  | 2026-06-30 | House | 3 |  | 2 |  | 1 |  |  |  | State
Middleton Road | Dunedin | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2023-11-20 |  |  | 2026-06-30 | House | 9 |  | 5 | 2 | 2 |  |  |  | State
Christian Street | Bryndwr | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-08-15 | 2024-04-22 |  | 2026-06-30 | House | 7 | 7 | [6 empty] | State
Tennyson Road | Hamilton | Hamilton City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-11 |  |  | 2026-06-30 | House | 18 |  | 8 | 4 | 6 |  |  |  | State
Godley Street | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-01 |  |  | 2026-06-30 | House | 3 |  | 2 | 1 |  |  |  |  | State
Shakespeare Avenue | Upper Hutt | Upper Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-23 |  |  | 2026-06-30 | Mixed | 3 |  |  |  | 3 |  |  |  | State
Fergusson Drive | Upper Hutt | Upper Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-06-18 | 2024-03-15 |  | 2026-06-30 | Mixed | 3 |  | 2 | 1 |  |  |  |  | State
Tindall Ave & Garret Place | Otara | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-02-29 | 2024-03-05 |  | 2026-06-30 | House | 6 |  | 2 |  | 4 |  |  |  | State
Nile Street | Nelson | Nelson City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-04-29 | 2024-05-27 |  | 2025-09-22 | Duplex | 10 |  |  |  | 10 |  |  |  | State
Nile Street | Nelson | Nelson City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-04-29 | 2024-05-27 |  | 2025-09-22 | Walk-up | 6 |  |  | 6 |  |  |  |  | State
Blenheim Road & Arthur Street | Riccarton | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-04-30 | Duplex | 10 |  |  | 10 |  |  |  |  | State
Blenheim Road & Arthur Street | Riccarton | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-04-30 | House | 10 |  |  | 2 | 2 | 5 | 1 |  | State
Blenheim Road & Arthur Street | Riccarton | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-04-30 | Terrace | 13 |  |  | 13 |  |  |  |  | State
Blenheim Road & Arthur Street | Riccarton | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-04-30 | Walk-up | 11 |  | 11 | [5 empty] | State
Bellona Place | Porirua | Porirua City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-11-05 | Terrace | 9 |  |  | 7 | 2 |  |  |  | State
Castor Cres | Porirua | Porirua City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-04 | Duplex | 6 |  |  | 6 |  |  |  |  | State
Castor Cres | Porirua | Porirua City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-04 | House | 2 |  |  |  |  | 2 |  |  | State
Castor Cres | Porirua | Porirua City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-08-04 | Walk-up | 6 |  |  | 6 |  |  |  |  | State
Crewe Cres | Palmerston North | Palmerston North City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 7 |  | 4 | 2 | 1 |  |  |  | State
Wayside | Wellington | Wellington City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 1 |  |  | 1 |  |  |  |  | State
Seddon Street | Lower Hutt | Lower Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-05-02 | 2024-07-16 |  | 2026-06-30 | House | 3 |  | 2 |  | 1 |  |  |  | State
Turner Drive | Rotorua | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-29 | 2024-01-24 |  | 2026-06-30 | House | 3 |  | 2 | 1 |  |  |  |  | State
Thomas Crescent | Rotorua | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-05-06 | 2024-05-15 |  | 2026-06-30 | Mixed | 6 |  | 4 |  | 1 | 1 |  |  | State
Kea Street | Rotorua | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 2 |  | 1 |  |  |  | State
Haddon Street | Mangere | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 2 |  |  |  |  | 2 |  |  | State
Raglan Street | Mangere | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 2 |  |  |  | 1 | 1 |  |  | State
Fergusson Drive | Upper Hutt | Upper Hutt City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-04-24 | 2024-05-21 |  | 2026-06-30 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State
Robyn Place | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-10 | 2023-11-13 |  | 2026-06-30 | House | 1 |  |  |  | 1 | 1 |  |  | State
Milton Road | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-11-01 | 2024-03-15 |  | 2026-06-30 | House | 1 | [5 empty] | 1 |  | State
Gray Avenue | Papatoetoe | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 1 |  |  |  |  | 1 |  |  | State
Calvert Avenue | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-06-27 | 2024-06-20 |  | 2026-06-30 | Duplex | 2 |  |  |  | 2 |  |  |  | State
Doon Street | Mosgiel | Dunedin City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 | 3 | [6 empty] | State
Doon Street & High Street | Mosgiel | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-04-24 |  |  | 2026-06-30 | Mixed | 8 |  | 4 | 3 | 1 |  |  |  | State
Tuata Street | One Tree Hill | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 8 |  |  |  | 6 | 6 | 1 |  | State
Worth Street | Kaitaia | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 6 |  | 4 |  |  | 2 |  |  | State
Wilkinson Avenue | Whangarei | Whangarei District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 6 |  |  | 6 |  |  |  |  | State
Whakatiki Street | Upper Hutt | Upper Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 6 |  | 2 | 2 | 2 |  |  |  | State
Longfellow Street | Upper Hutt | Upper Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 | 2 | 1 | [5 empty] | State
Mount View Drive | Mangakakahi | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-07-30 | 2024-08-07 |  | 2026-06-30 | Mixed | 3 |  | 2 |  | 1 |  |  |  | State
Corilin Place | Mangakakahi | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-07-03 | 2024-07-01 |  | 2026-06-30 | House | 3 |  | 2 | 1 |  |  |  |  | State
Milton Grove | Owhata | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-10-09 | House | 3 |  |  | 2 |  |  | 1 |  | State
Clayton Road | Mangakakahi | Rotorua District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 14 |  | 11 | 1 | 2 |  |  |  | State
Redgrave Street | Christchurch | Christchurch City | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2023-08-18 | 2023-09-29 |  | 2026-06-30 | House | 3 | 3 | [6 empty] | State
Green Street | Mosgiel | Dunedin City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-08-12 |  |  | 2026-06-30 | Mixed | 6 |  | 4 | 2 |  |  |  |  | State
MacDonald Street | Timaru | Timaru District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-06-27 |  |  | 2026-06-30 | House | 2 |  | 2 | [5 empty] | State
George Street | Lower Hutt | Lower Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 2 |  |  |  | 2 |  |  |  | State
Garnet Place | Rotorua | Rotorua District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-08-20 | 2024-07-17 |  | 2026-06-30 | House | 2 |  |  |  | 1 | 1 |  |  | State
Delhi Avenue | Whanganui | Whanganui District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 10 |  | 8 | 2 |  |  |  |  | State
Windrush Close | Mangere | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-31 |  |  | 2026-06-30 | House | 2 |  |  |  |  | 2 |  |  | State
Tupoki Street | New Plymouth | New Plymouth District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 4 |  | 2 | 2 |  |  |  |  | State
Monmouth Street | Feilding | Manawatu District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 4 |  | 4 | [5 empty] | State
Glen Street | Timaru | Timaru District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-06-19 | 2024-06-21 |  | 2026-06-30 | House | 3 |  | 1 | 2 |  |  |  |  | State
Selwyn Street | Timaru | Timaru District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 3 |  | 3 | [5 empty] | State
Tyne Street | Timaru | Timaru District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-06-24 | 2024-08-05 |  | 2026-06-30 | House | 3 |  | 3 | [5 empty] | State
Ewenson Avenue | One Tree Hill | Auckland | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-07-05 |  |  | 2026-06-30 | House | 3 |  |  |  | 2 | 1 |  |  | State
Waikare Road | Kawakawa | Far North District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 1 |  |  | 1 |  |  |  |  | State
Woodward Street | Featherston | South Wairarapa District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-03-31 | House | 7 |  |  | 3 | 3 | 1 |  |  | State
Waimea Road | Nelson | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 8 |  | 8 | [5 empty] | State
Pleiades Street | Waitara | New Plymouth District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 1 |  |  |  | 1 |  |  |  | State
Kauri Street | New Plymouth | New Plymouth District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 1 |  |  |  | 1 |  |  |  | State
Edinburgh Street | Feliding | Manawatu District | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-13 |  |  | 2026-06-30 | House | 2 |  |  |  | 2 |  |  |  | State
Ohauiti Road | Tauranga | Tauranga City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 2 | 1 |  |  |  |  | State
Kiwi Street | Kaikoura | Kaikoura District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-09-02 | 2024-08-01 |  | 2026-06-30 | House | 2 |  | 1 | 1 |  |  |  |  | State
Seaview Road | Stoke | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 2 |  | 2 | [5 empty] | State
Warden Street | Richmond | Upper Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 6 |  | 4 | 2 |  |  |  |  | State
Flinders Place | Tauranga | Tauranga City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 2 | 1 |  |  |  |  | State
Jonathon Street | Tauranga | Tauranga City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Duplex | 5 |  | 2 | 2 | 1 |  |  |  | State
Jonathon Street | Tauranga | Tauranga City | Consented Not Contracted | Under Review | Redevelopment | Yes | No | 2024-09-20 |  |  | 2026-06-30 | Duplex | 3 |  | 2 | 1 |  |  |  |  | State
Sutherland Road | Tauranga | Tauranga City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 5 |  | 4 |  | 1 |  |  |  | State
Warden Road | Christchurch | Christchurch City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2025-09-30 | House | 2 |  | 2 | [5 empty] | State
Alford Street | Waterview | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  |  |  | 3 |  |  |  | State
Henwood Road & Mayflower Close | Mangere | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 14 |  |  | 2 | 5 | 5 | 2 |  | State
Fergusson Drive | UpperHutt | Upper Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  |  |  | 3 |  |  |  | State
Taharepa Road | Taupo | Taupo District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 2 |  |  | 1 |  |  | State
Richmond Avenue | Taupo | Taupo District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 5 |  | 4 | 1 |  |  |  |  | State
Opua Street | Belmont | Auckland | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 4 |  |  | 2 | 2 | 2 |  |  | State
Kauri Street | Stoke | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 6 |  | 6 | [5 empty] | State
Orchard Road | Stoke | Nelson City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Mixed | 8 |  | 8 | [5 empty] | State
Ward Street | Upper Hutt | Upper Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | Duplex | 5 |  | 5 | [5 empty] | State
Sim Street | Ngaruawahia | Waikato District | Consented Not Contracted | Under Review | Redevelopment | Yes | Yes | 2024-09-03 | 2024-08-21 |  | 2026-06-30 | House | 1 |  |  |  | 1 |  |  |  | State
Molesworth Street | Lower Hutt | Lower Hutt City | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 2 |  | 1 |  |  |  | State
Pihanga Street | Taupo | Taupo District | In Progress, Not Consented | Under Review | Redevelopment | No | No |  |  |  | 2026-06-30 | House | 3 |  | 2 |  |  | 1 |  |  | State